## SWA(summary)
SUMMARY OF CLUSTER SWA
Period Covered From __________________ to ___________________
CLUSTER NO.: _______
(sample only)
Project | :
Contract No. | :
Contractor | :
Region | :
Division/s | :
Name of School |  | Municipality/ City | Amount | Equivalent Weight % (A) | Accomplishment (%) |  |  |  | UNIT COST |  | COST |  | TOTAL
[5 empty] | Previous (B) | This Period ( C ) | To Date (D) | E=(A)*(D) | UNIT COST | UNIT COST | UNIT COST | UNIT COST
School A |  |  | 1000000 | 0.25 |  | 50 | 50 | 12.5
School B |  |  | 1000000 | 0.25 |  | 50 | 50 | 12.5
School C |  |  | 1000000 | 0.25 |  | 50 | 50 | 12.5 |  | 7100 |  | 7100
School D |  |  | 1000000 | 0.25 |  | 50 | 50 | 12.5 | MATERIAL | LABOR | MATERIAL | LABOR
|  |  | 4000000 | 1
Total Accomplishment (Cluster) %: | [7 empty] | 50
[11 empty] | 0 | 5000 | 5000
Prepared by: | [5 empty] | Recommending Approval: | [7 empty] | #VALUE!
#VALUE!
DepEd Project Engineer | [5 empty] | Chief, ESSD/Governance
Approved:
Head, Procuring Entity

## SWA(per school)
PROJECT | STATEMENT OF WORK ACCOMPLISHMENT
LOCATION | Period Covered From __________________ to ___________________
(sample only)
| Project |  | :
| Cluster No. |  | :
| Contract No. |  | :
| Contractor |  | :
| Region |  | :
SUBJECT | Division |  | :
| Municipality |  | :
| Name of School |  | :
ITEM NO. | ITEM/DESCRIPTION |  |  | UNIT | QTY | Equivalent Weight (A) | Equivalent Weight (A) | Accomplishment (%) |  |  |  | UNIT COST |  | COST |  | TOTAL
[12 empty] | UNIT COST | UNIT COST | UNIT COST | UNIT COST
[13 empty] | 7100 |  | 7100
[8 empty] | Prev. (B) | This Period (C) | To-Date (D)=(B+C) | (E)=(A*D) | MATERIAL | LABOR | MATERIAL | LABOR
| I. | GENERAL REQUIREMENTS
|  | Mobilization/Demobilization and temfacil. |  | lot | 1 | 0.017827 | 0.017827 | [6 empty] | 0 | 5000 | 5000
|  | Sub-total | [13 empty] | 5000 | 5000
| II. | CIVIL WORKS
| A. | Earthworks
|  | Clearing,grubbing and waste disposal |  | m2 | 81 | 0.0056315 | 0.0056315 |  |  |  |  | 15 | 4.5 | 1215 | 364.5 | 1579.5
|  | Excavation |  | m3 | 14.69 | 0.0052376 | 0.0052376 | [5 empty] | 100 | 0 | 1469 | 1469
|  | Backfill/Compacting |  | m3 | 8.79 | 0.0018804 | 0.0018804 | [5 empty] | 60 | 0 | 527.4 | 527.4
|  | Select Fill |  | m3 | 3 | 0.001752 | 0.001752 |  |  |  |  | 126 | 37.8 | 378 | 113.4 | 491.4
|  | Gravel bed, G-1 |  | m3 | 3.6 | 0.010012 | 0.010012 |  |  |  |  | 600 | 180 | 2160 | 648 | 2808
|  | Sub-total | [13 empty] | 6875.3 | 6875.3
| B. | Concreting
|  | Column Footing |  | m3 | 1.46 | 0.016269
|  | Portland Cement |  | bags | 14 |  | 0.0090846 |  |  |  |  | 140 | 42 | 1960 | 588 | 2548
|  | Wash Sand |  | m3 | 1 |  | 0.0016223 |  |  |  |  | 350 | 105 | 350 | 105 | 455
|  | Gravel, G-1 |  | m3 | 2 |  | 0.005562 |  |  |  |  | 600 | 180 | 1200 | 360 | 1560
|  | Wall Footing |  | m3 | 3.2 | 0.026002
|  | Portland Cement |  | bags | 29 |  | 0.018818 |  |  |  |  | 140 | 42 | 4060 | 1218 | 5278
|  | Wash Sand |  | m3 | 1 |  | 0.0016223 |  |  |  |  | 350 | 105 | 350 | 105 | 455
|  | Gravel, G-1 |  | m3 | 2 |  | 0.005562 |  |  |  |  | 600 | 180 | 1200 | 360 | 1560
|  | Column |  | m3 | 1.638 | 0.017845
|  | Portland Cement |  | bags | 15 |  | 0.0097335 |  |  |  |  | 140 | 42 | 2100 | 630 | 2730
|  | Wash Sand |  | m3 | 1 |  | 0.0016223 |  |  |  |  | 350 | 105 | 350 | 105 | 455
|  | Gravel, 3/4 |  | m3 | 2 |  | 0.006489 |  |  |  |  | 700 | 210 | 1400 | 420 | 1820
|  | Beams |  | m3 | 2.1 | 0.02044
|  | Portland Cement |  | bags | 19 |  | 0.012329 |  |  |  |  | 140 | 42 | 2660 | 798 | 3458
|  | Wash Sand |  | m3 | 1 |  | 0.0016223 |  |  |  |  | 350 | 105 | 350 | 105 | 455
|  | Gravel, 3/4 |  | m3 | 2 |  | 0.006489 |  |  |  |  | 700 | 210 | 1400 | 420 | 1820
|  | Slab on Fill |  | m3 | 8.13 | 0.062735
|  | Portland Cement |  | bags | 49 |  | 0.031796 |  |  |  |  | 140 | 42 | 6860 | 2058 | 8918
|  | Wash Sand |  | m3 | 4.5 |  | 0.0073002 |  |  |  |  | 350 | 105 | 1575 | 472.5 | 2047.5
|  | Gravel, G-1 |  | m3 | 8.5 |  | 0.023639 |  |  |  |  | 600 | 180 | 5100 | 1530 | 6630
|  | Sub-total | [13 empty] | 40189.5 | 40189.5
| C. | Rebars
|  | Footing |  | kgs | 132.58 | 0.0094635 | 0.0094635 |  |  |  |  | 14.3 | 5.72 | 1895.894 | 758.3576 | 2654.2516
|  | Wall Footing |  | kgs | 96.2 | 0.0063762 | 0.0063762 |  |  |  |  | 14.3 | 4.29 | 1375.66 | 412.698 | 1788.358
|  | Column |  | kgs | 503.72 | 0.035955 | 0.035955 |  |  |  |  | 14.3 | 5.72 | 7203.196 | 2881.2784 | 10084.4744
|  | Beams |  | kgs | 366.14 | 0.026135 | 0.026135 |  |  |  |  | 14.3 | 5.72 | 5235.802 | 2094.3208 | 7330.1228
|  | Slab on Fill |  | kgs | 185 | 0.012262 | 0.012262 |  |  |  |  | 14.3 | 4.29 | 2645.5 | 793.65 | 3439.15
|  | Sub-total | [13 empty] | 25296.3568 | 25296.3568
| . |  | . | . |  |  |  | . |  |  | .
| D. | Formworks/scaffoldings (two uses)
|  | Column |  | m2 | 31.92 | 0.021219
|  | 1/4" thk. Ordinary Plywood |  | pcs | 11 |  | 0.0064241 |  |  |  |  | 126 | 37.8 | 1386 | 415.8 | 1801.8
|  | Coco lumber |  | bd.ft. | 798 |  | 0.014795 |  |  |  |  | 4 | 1.2 | 3192 | 957.6 | 4149.6
|  | Beams |  | m2 | 33.7 | 0.031982
|  | 1/4" thk. Ordinary Plywood |  | pcs | 28 |  | 0.016352 |  |  |  |  | 126 | 37.8 | 3528 | 1058.4 | 4586.4
|  | Coco lumber |  | bd.ft. | 843 |  | 0.015629 |  |  |  |  | 4 | 1.2 | 3372 | 1011.6 | 4383.6
|  | Sub-total | [13 empty] | 14921.4 | 14921.4
| E. | Masonry Works
|  | CHB 6" with Rebars |  | m2 | 91.08 | 0.084086
|  | 6" thk. CHB |  | pcs | 1139 |  | 0.034315 |  |  |  |  | 6.5 | 1.95 | 7403.5 | 2221.05 | 9624.55
|  | Portland Cement |  | bags | 45 |  | 0.029201 |  |  |  |  | 140 | 42 | 6300 | 1890 | 8190
|  | White Sand |  | m3 | 5 |  | 0.00927 |  |  |  |  | 400 | 120 | 2000 | 600 | 2600
|  | 10mmø x 6m deform bars |  | pcs | 46 |  | 0.0113 |  |  |  |  | 53 | 15.9 | 2438 | 731.4 | 3169.4
|  | Plastering |  | m2 | 182.16 | 0.051634
|  | Portland Cement |  | bags | 61 |  | 0.039583 |  |  |  |  | 140 | 42 | 8540 | 2562 | 11102
|  | White Sand |  | m3 | 6.5 |  | 0.012051 |  |  |  |  | 400 | 120 | 2600 | 780 | 3380
|  | Sub-total | [13 empty] | 38065.95 | 38065.95
| F. | Doors & Windows
1 |  | D - 1,Panel Door with transom on yakal or guijo jamb ( 1.0 x 2.4 m) |  | set | 2 | 0.025671 | 0.025671 |  |  |  |  | 3000 | 600 | 6000 | 1200 | 7200
5 |  | W - 1, ( 2.6 x 1.6 m) Clear glass jalousie window on standard aluminum housing with fixed clear glass transom on yakal or guijo wooden jamb. |  | set | 2 | 0.037805 | 0.037805 |  |  |  |  | 4418 | 883.6 | 8836 | 1767.2 | 10603.2
6 |  | W - 2, (1.3 x 1.6 m) Clear glass jalousie window on standard aluminum housing with fixed clear glass transom on yakal or guijo wooden jamb. |  | set | 2 | 0.03279 | 0.03279 |  |  |  |  | 3832 | 766.4 | 7664 | 1532.8 | 9196.8
|  | Decorative blocks |  | pcs. | 12 | 0.0010268 | 0.0010268 |  |  |  |  | 20 | 4 | 240 | 48 | 288
|  | Sub-total | [13 empty] | 27288 | 27288
| F. | Roofing & Accessories
|  | Corr. GI Sht #26 x12' |  | pcs. | 17 | 0.019856 | 0.019856 |  |  |  |  | 252 | 75.6 | 4284 | 1285.2 | 5569.2
|  | Corr. GI Sht #26 x 9' |  | pcs. | 34 | 0.029785 | 0.029785 |  |  |  |  | 189 | 56.7 | 6426 | 1927.8 | 8353.8
|  | Corr. GI Sht #26 x 10' |  | pcs. | 17 | 0.016547 | 0.016547 |  |  |  |  | 210 | 63 | 3570 | 1071 | 4641
|  | Ridge Roll #26 |  | pcs. | 5 | 0.002781 | 0.002781 |  |  |  |  | 120 | 36 | 600 | 180 | 780
|  | Flashing #26 x 8' |  | pcs. | 10 | 0.005562 | 0.005562 |  |  |  |  | 120 | 36 | 1200 | 360 | 1560
|  | Teckscrew 2 1/2" |  | pcs. | 612 | 0.0070916 | 0.0070916 |  |  |  |  | 2.5 | 0.75 | 1530 | 459 | 1989
|  | Facia Board |  | bf | 148 | 0.024695 | 0.024695 |  |  |  |  | 36 | 10.8 | 5328 | 1598.4 | 6926.4
|  | Roof Sealant |  | qrt. | 1 | 0.00069525 | 0.00069525 |  |  |  |  | 150 | 45 | 150 | 45 | 195
|  | Sub-total | [13 empty] | 30014.4 | 30014.4
| G. | Structural Steel Works
|  | `150 x 65 x 20 x 3 mm LC Structural Steel Rafters |  | kgs. | 485 | 0.040464 | 0.040464 |  |  |  |  | 18 | 5.4 | 8730 | 2619 | 11349
|  | 100 x 50 x 15 x 1.5 mm LC Structural Steel Purlins |  | kgs. | 400.5 | 0.033414 | 0.033414 |  |  |  |  | 18 | 5.4 | 7209 | 2162.7 | 9371.7
3 |  | 10mmø sag rods (0.75m length) with standard nuts and washer @ each end |  | pcs | 26 | 0.0013905 | 0.0013905 |  |  |  |  | 10 | 5 | 260 | 130 | 390
4 |  | 10mmø tie rods |  | pcs | 4 | 0.00014975 | 0.00014975 |  |  |  |  | 7 | 3.5 | 28 | 14 | 42
7 |  | 16mmø x 300mm long bent anchor bolts with nuts and washer |  | pcs | 24 | 0.016173 | 0.016173 |  |  |  |  | 126 | 63 | 3024 | 1512 | 4536
8 |  | 10mmø x 150mm long bent anchor bolts with nuts and washer |  | pcs | 30 | 0.0040111 | 0.0040111 |  |  |  |  | 25 | 12.5 | 750 | 375 | 1125
9 |  | 4' x 8" x 9mm steel plate (for base plate) |  | pcs | 1 | 0.022446 | 0.022446 |  |  |  |  | 4197 | 2098.5 | 4197 | 2098.5 | 6295.5
11 |  | Welding Rod |  | kgs. | 40 | 0.013905 | 0.013905 |  |  |  |  | 65 | 32.5 | 2600 | 1300 | 3900
|  | B.I. Pipe 100mm dia (sched. 40) |  | pcs. | 2 | 0.008343 | 0.008343 |  |  |  |  | 900 | 270 | 1800 | 540 | 2340
|  | Sub-total | [13 empty] | 39349.2 | 39349.2
I. | H. | Ceiling Works
1 |  | Interior ceiling |  | m2 | 72 | 0.056322
|  | Cieling joist/hangers |  | bd ft | 275.31 |  | 0.030626 |  |  |  |  | 24 | 7.2 | 6607.44 | 1982.232 | 8589.672
|  | Ordinary Plywood 1/4" thk. |  | pcs | 22 |  | 0.025697 |  |  |  |  | 252 | 75.6 | 5544 | 1663.2 | 7207.2
|  | Sub-total | [13 empty] | 15796.872 | 15796.872
J. | I. | Painting Works
1 |  | Concrete surfaces |  | m2 | 182.16 | 0.041194
|  | Concrete neutralizer |  | gal. | 7.5 |  | 0.0095597 |  |  |  |  | 275 | 82.5 | 2062.5 | 618.75 | 2681.25
|  | Latex primer |  | gal. | 7.5 |  | 0.0097335 |  |  |  |  | 280 | 84 | 2100 | 630 | 2730
|  | Patching Compound |  | gal. | 7.5 |  | 0.010429 |  |  |  |  | 300 | 90 | 2250 | 675 | 2925
|  | Semigloss latex |  | gal. | 7.5 |  | 0.011472 |  |  |  |  | 330 | 99 | 2475 | 742.5 | 3217.5
2 |  | Wood surfaces (plywood ceiling) |  | m2 | 72 | 0.014484
|  | Flat wall enamel |  | gal. | 3 |  | 0.0041715 |  |  |  |  | 300 | 90 | 900 | 270 | 1170
|  | Glazing putty |  | gal. | 3 |  | 0.0050058 |  |  |  |  | 360 | 108 | 1080 | 324 | 1404
|  | Quick dry enamel (QDE) |  | gal. | 3 |  | 0.0048668 |  |  |  |  | 350 | 105 | 1050 | 315 | 1365
|  | Paint thinner |  | gal. | 1 |  | 0.00044033 |  |  |  |  | 95 | 28.5 | 95 | 28.5 | 123.5
3 |  | Wood surfaces (doors and windows) |  | m2 | 13 | 0.015794
|  | Flat wall enamel |  | gal. | 0.75 |  | 0.0010429 |  |  |  |  | 300 | 90 | 225 | 67.5 | 292.5
|  | Glazing putty |  | gal. | 0.75 |  | 0.0012515 |  |  |  |  | 360 | 108 | 270 | 81 | 351
|  | Quick dry enamel (QDE) |  | gal. | 0.75 |  | 0.0012167 |  |  |  |  | 350 | 105 | 262.5 | 78.75 | 341.25
|  | Paint thinner |  | gal. | 1 |  | 0.00044033 |  |  |  |  | 95 | 28.5 | 95 | 28.5 | 123.5
4 |  | Roofing & Accessories |  | m2 | 115.44 |  | 0
|  | Zinc chromate |  | gal. | 3 |  | 0.005562 |  |  |  |  | 400 | 120 | 1200 | 360 | 1560
|  | Portland cement roof paint, green boysen |  | gal. | 3 |  | 0.0058401 |  |  |  |  | 420 | 126 | 1260 | 378 | 1638
|  | Paint thinner |  | gal. | 1 |  | 0.00044033 |  |  |  |  | 95 | 28.5 | 95 | 28.5 | 123.5
|  | Sub-total | [13 empty] | 20046 | 20046
| J. | ELECTRICAL WORKS
Roughing-ins
|  | 15 mmø PVC Conduit, Sch. 40 |  | pcs | 20 | 0.004635 | 0.004635 |  |  |  |  | 50 | 15 | 1000 | 300 | 1300
|  | 20 mmø RSC |  | pc | 1 | 0.0026883 | 0.0026883 |  |  |  |  | 580 | 174 | 580 | 174 | 754
|  | 20 mmø Type F Condulet |  | pc | 1 | 0.00069525 | 0.00069525 |  |  |  |  | 150 | 45 | 150 | 45 | 195
|  | 20 mmø Entrance Cap |  | pc | 1 | 0.00034763 | 0.00034763 |  |  |  |  | 75 | 22.5 | 75 | 22.5 | 97.5
|  | 4" x 4" Junction box, G.I. |  | pcs | 6 | 0.00069525 | 0.00069525 |  |  |  |  | 25 | 7.5 | 150 | 45 | 195
|  | 2" x 4" Utility box, G.I. |  | pcs | 4 | 0.0004635 | 0.0004635 |  |  |  |  | 25 | 7.5 | 100 | 30 | 130
|  | 16 mmø x 2.4 m Grounding Rod |  | pc | 1 | 0.00069525 | 0.00069525 |  |  |  |  | 150 | 45 | 150 | 45 | 195
Wires & Fixtures
|  | 3.5 mm2 THW Wire, Stranded |  | lm | 180 | 0.0075087 | 0.0075087 |  |  |  |  | 9 | 2.7 | 1620 | 486 | 2106
|  | 10 A, Duplex C.O. w/ Cover |  | sets | 2 | 0.0008343 | 0.0008343 |  |  |  |  | 90 | 27 | 180 | 54 | 234
|  | 10 A, 3-Gang Switch w/ Cover |  | set | 1 | 0.0005562 | 0.0005562 |  |  |  |  | 120 | 36 | 120 | 36 | 156
|  | 2 x 40 W Industrial Type FL |  | sets | 4 | 0.017613 | 0.017613 |  |  |  |  | 950 | 285 | 3800 | 1140 | 4940
|  | 50 W Incandescent Bulb |  | pc | 1 | 0.00016223 | 0.00016223 |  |  |  |  | 35 | 10.5 | 35 | 10.5 | 45.5
|  | Porcelain Receptacle |  | pc | 1 | 0.00013905 | 0.00013905 |  |  |  |  | 30 | 9 | 30 | 9 | 39
|  | 30 A, 2PST, 250 V Safety Switch |  | set | 1 | 0.0016223 | 0.0016223 |  |  |  |  | 350 | 105 | 350 | 105 | 455
|  | Electrical Tape |  | roll | 1 | 0.00011588 | 0.00011588 |  |  |  |  | 25 | 7.5 | 25 | 7.5 | 32.5
|  | Sub-total | [13 empty] | 10874.5 | 10874.5
| K. | Others
|  | Common Wire Nail (Asstd.) |  | kgs | 25 | 0.0033693 | 0.0033693 |  |  |  |  | 31.5 | 6.3 | 787.5 | 157.5 | 945
|  | GI Wire # 16 |  | kgs | 14 | 0.0020965 | 0.0020965 |  |  |  |  | 35 | 7 | 490 | 98 | 588
|  | Barrel bolt or lockset |  | sets | 2 | 0.0015403 | 0.0015403 |  |  |  |  | 180 | 36 | 360 | 72 | 432
|  | LP Hinges 31/2 x 31/2 |  | prs | 8 | 0.001198 | 0.001198 |  |  |  |  | 35 | 7 | 280 | 56 | 336
|  | Soil poisoning and wood preservatives |  | m2 | 81 | 0.015884 | 0.015884 |  |  |  |  | 50 | 5 | 4050 | 405 | 4455
|  | Sub-total | [13 empty] | 6756 | 6756
|  | DIRECT COST | [13 empty] | 280473.4788 | 280473.4788
|  | INDIRECT COST @ 31% | [13 empty] | 86946.7784
|  | TOTAL CONST. COST | [13 empty] | 367420.2572
| TOTAL ACCOMPLISHMENT |  |  |  |  | 1 | 1
| Prepared by: | [7 empty] | Reviewed: | [7 empty] | 367420.2572
4536.0526
| Contractor's Representative | [7 empty] | DepEd Project Engineer
| Recommending Approval: | [7 empty] | Approved:
| Chief, ESSD/Governance | [7 empty] | Head, Procuring Entity
3001
3002
3011
3012
3031
3032
3041
3051
3061
3071
3081
3091
3101
3111
3121
3122
3123
3131
3141
3151
3161
3171