## COP DO
Republic of the Philippines
DEPARTMENT OF EDUCATION
Physical Facilities and Schools Engineering Division
Regional Office No. ________________________
Division of ________________________
CERTIFICATE OF PAYMENT
| Project Name |  | : |  |  |  |  | COP No. | :
| Cluster No. |  | : |  |  |  |  | Period Covered | :
| School/s |  | : |  |  |  |  | Remarks
| Contractor |  | :
CONSTRUCTION CONTRACT DATA/INFORMATION
| Original Contract Amount |  |  |  | P |  |  | Original Construction Period
| Extra Work Order Amount |  |  |  | P |  |  | Addt'l Construction Period
| Revised Contract Amount |  |  |  | P |  |  | Revised Construction Period
| % of Contract Paid | [6 empty] | % of Time Elapsed
| % of Work Done |  |  |  | Previous: |  | This Period: |  | To date:
| 1. | Revised Contract Amount ………………………………………………………………………….. | [6 empty] | P
| 2. | Advance Payment (AP) ……………………………………………………………………………… | [6 empty] | P
|  | a. Previous Recoupment/s ………………………………… |  |  |  |  | P
|  | b. Balance of AP …………………………………………… |  |  |  |  | P
| 3. | Previous Certificate/s ………………………………………………………………………………. | [6 empty] | P
|  | a. Cumulative Retention ……………………………………. |  |  |  |  | P
b. Cumulative W/Holding Tax …………………………….
c. Cumulative VAT …………………………………………
d. Cumulative AP Recoupment ……………………………
e. Liquidated Damages …………………………………….
f. Others ……………………………………………………..
|  | TOTAL DEDUCTION |  |  |  |  | P
|  | NET AMOUNT RECEIVED |  |  |  |  | P
| 4. | Balance Before this Certificate …………………………………………………………………… | [6 empty] | P
| 5. | This Certificate | [6 empty] | P
|  | a. Retention (10%) …………………………………………. |  |  |  |  | P
b. W/Holding Tax (2%) …………………………………….
c. Value Added Tax …………………………………………
|  | d. AP Recoupment …………………………………………. | [8 empty] | 0 | 0
e. Liquidated Damages ……………………………………..
f. Others ……………………………………………………..
|  | TOTAL DEDUCTION …………………………………….. |  |  |  |  | P |  |  |  | 0
|  | NET AMOUNT RECEIVED ………………………………. |  |  |  |  | P
| 6. | Balance After this Certificate …………………………………………………………………….. | [6 empty] | P
Amount Due and Payable This Certificate (in words):
Prepared by: | [5 empty] | Recommending Approval: |  |  | Approved:
Project Engineer | [5 empty] | Resource Mobilization & Governance Chief |  |  | Schools Division Superintendent
ATTACHMENT:
|  |  | - | Summary of Cluster SWA | [5 empty] | Date
|  |  | - | Statement of Work Accomplishment (SWA) per school
|  |  | - | Progress Photographs

## COP-SUMAG
CERTIFICATE OF PAYMENT
| Project Name |  | : | Construction of one (1) Unit 1STY1CL Pre-School Building | [6 empty] | COP No. |  | : | 1
| Cluster No. |  | : | [7 empty] | Period Covered |  | :
| School/s |  | : | Southern Conner Central School | [6 empty] | Remarks |  |  | Final Billing
| Contractor |  | : | Sumag Builder and Construction
CONSTRUCTION CONTRACT DATA/INFORMATION
| Original Contract Amount |  |  |  | P | 816301.35 |  |  |  |  | Original Construction Period |  |  |  | 60 CD
| Extra Work Order Amount |  |  |  | P | [5 empty] | Addt'l Construction Period
| Revised Contract Amount |  |  |  | P | [5 empty] | Revised Construction Period
| % of Contract Paid | [9 empty] | % of Time Elapsed
| % of Work Done |  |  |  | Previous: |  | 0 |  | This Period: |  | 100% |  | To date: |  | 100%
| 1. | Total Contract Amount ………………………………………………………………………….. | [10 empty] | P | 816301.35
| 2. | Advance Payment (AP) ……………………………………………………………………………… | [10 empty] | P
|  | a. Previous Recoupment/s ………………………………… | [6 empty] | P
|  | b. Balance of AP …………………………………………… | [6 empty] | P
| 3. | Previous Certificate/s ………………………………………………………………………………. | [10 empty] | P
|  | a. Cumulative Retention ……………………………………. | [6 empty] | P
b. Cumulative W/Holding Tax …………………………….
c. Cumulative VAT …………………………………………
d. Cumulative AP Recoupment ……………………………
e. Liquidated Damages …………………………………….
f. Others ……………………………………………………..
|  | TOTAL DEDUCTION | [6 empty] | P
|  | NET AMOUNT RECEIVED | [6 empty] | P
| 4. | Balance Before this Certificate …………………………………………………………………… | [10 empty] | P | 816301.35
| 5. | This Certificate | [10 empty] | P | 816301.35
|  | a. Retention (10%) …………………………………………. | [6 empty] | P
|  | b. W/Holding Tax (1.786%) ……………………………………. | [7 empty] | 14576.8098
|  | c. Value Added Tax (4.464%)…………………………………… | [7 empty] | 40086.227
d. AP Recoupment ………………………………………….
|  | e. Liquidated Damages …………………………………….. | [7 empty] | 38718.32
f. Others ……………………………………………………..
|  | TOTAL DEDUCTION …………………………………….. | [6 empty] | P | 93381.3568
|  | NET AMOUNT RECEIVED ………………………………. | [6 empty] | P | 722919.9932
| 6. | Balance After this Certificate …………………………………………………………………….. | [10 empty] | P | 722919.9932
| Amount Due and Payable This Certificate (in words): | [6 empty] | SEVEN HUNDRED TWENTY TWO THOUSAND NINE HUNDRED
NINETEEN AND 99/100 PESOS
Prepared by: | [5 empty] | Recommending Approval: | [5 empty] | Approved:
CHRISTOPHER B. HADSAN | [5 empty] | AGUSTIN B. GUMUWANG, Ph.D. | [5 empty] | ELLEN B. DONATO Ed.D., CESO III
DepEd Project Engineer | [5 empty] | Chief, ESSD | [6 empty] | Head, Procuring Entity
ATTACHMENT:
|  |  | - | Summary of Cluster SWA | [9 empty] | Date
|  |  | - | Statement of Work Accomplishment (SWA) per school
|  |  | - | Progress Photographs

## COP-APAYAO
CERTIFICATE OF PAYMENT
| Project Name |  | : | Supply and Delivery of School Furniture for the SHS Program under the 15% Regional Office Allocation from the CY-2014 BEFF-Lot 2 (Apayao Division) | [6 empty] | COP No. |  | : | 1
| Cluster No. |  | : | 2 | [6 empty] | Period Covered |  | :
| School/s |  | : | Division of Apayao | [6 empty] | Remarks |  |  | Final Billing
| Contractor |  | : | Sumag Builder and Construction
CONSTRUCTION CONTRACT DATA/INFORMATION
| Original Contract Amount |  |  |  | P | 2144000 |  |  |  |  | Original Construction Period |  |  |  | 120 CD
| Extra Work Order Amount |  |  |  | P | [5 empty] | Addt'l Construction Period
| Revised Contract Amount |  |  |  | P | [5 empty] | Revised Construction Period
| % of Contract Paid | [9 empty] | % of Time Elapsed
| % of Work Done |  |  |  | Previous: |  | 0 |  | This Period: |  | 100% |  | To date: |  | 100%
| 1. | Total Contract Amount ………………………………………………………………………….. | [10 empty] | P | 2144000
| 2. | Advance Payment (AP) ……………………………………………………………………………… | [10 empty] | P
|  | a. Previous Recoupment/s ………………………………… | [6 empty] | P
|  | b. Balance of AP …………………………………………… | [6 empty] | P
| 3. | Previous Certificate/s ………………………………………………………………………………. | [10 empty] | P
|  | a. Cumulative Retention ……………………………………. | [6 empty] | P
b. Cumulative W/Holding Tax …………………………….
c. Cumulative VAT …………………………………………
d. Cumulative AP Recoupment ……………………………
e. Liquidated Damages …………………………………….
f. Others ……………………………………………………..
|  | TOTAL DEDUCTION | [6 empty] | P
|  | NET AMOUNT RECEIVED | [6 empty] | P
| 4. | Balance Before this Certificate …………………………………………………………………… | [10 empty] | P | 2144000
| 5. | This Certificate | [10 empty] | P | 2144000
|  | a. Retention (10%) …………………………………………. | [6 empty] | P | 214400
b. W/Holding Tax (1.786%) …………………………………….
c. Value Added Tax (4.464%)……………………………………
d. AP Recoupment ………………………………………….
e. Liquidated Damages ……………………………………..
f. Others ……………………………………………………..
|  | TOTAL DEDUCTION …………………………………….. | [6 empty] | P | 214400
|  | NET AMOUNT RECEIVED ………………………………. | [6 empty] | P | 1929600
| 6. | Balance After this Certificate …………………………………………………………………….. | [10 empty] | P | 214400
| Amount Due and Payable This Certificate (in words): | [6 empty] | ONE MILLION NINE HUNDRED TWWENTY NINE THOUSAND
SIX HUNDRED PESOS ONLY
Prepared by: | [5 empty] | Recommending Approval: | [5 empty] | Approved:
CHRISTOPHER B. HADSAN | [5 empty] | AGUSTIN B. GUMUWANG, Ph.D. | [5 empty] | ELLEN B. DONATO Ed.D., CESO III
DepEd Project Engineer | [5 empty] | Chief, ESSD | [6 empty] | Regional Director
ATTACHMENT:
|  |  | - | Summary of Cluster SWA | [9 empty] | Date
|  |  | - | Statement of Work Accomplishment (SWA) per school
|  |  | - | Progress Photographs

## Bontoc CS
CERTIFICATE OF PAYMENT
| Project Name |  | : | Repair/Rehab of School Buildings in Various School Sites under the CY 2014 BEFF | [6 empty] | COP No. |  | : | 1
| Cluster No. |  | : | 4A | [6 empty] | Period Covered |  | :
| School/s |  | : | Division of Mountain Province | [6 empty] | Remarks |  |  | 1st Progress Billing
| Contractor |  | : | Polo Engineering & Construction
CONSTRUCTION CONTRACT DATA/INFORMATION
| Original Contract Amount |  |  |  | P | 2047366.03 |  |  |  |  | Original Construction Period |  |  |  | 90 CD
| Extra Work Order Amount |  |  |  | P | [5 empty] | Addt'l Construction Period
| Revised Contract Amount |  |  |  | P | [5 empty] | Revised Construction Period
| % of Contract Paid | [9 empty] | % of Time Elapsed
| % of Work Done |  |  |  | Previous: |  | 0 |  | This Period: |  | 76.75% |  | To date: |  | 76.75%
| 1. | Total Contract Amount ………………………………………………………………………….. | [10 empty] | P | 2047366.03
| 2. | Advance Payment (AP) ……………………………………………………………………………… | [10 empty] | P
|  | a. Previous Recoupment/s ………………………………… | [6 empty] | P
|  | b. Balance of AP …………………………………………… | [6 empty] | P
| 3. | Previous Certificate/s ………………………………………………………………………………. | [10 empty] | P
|  | a. Cumulative Retention ……………………………………. | [6 empty] | P
b. Cumulative W/Holding Tax …………………………….
c. Cumulative VAT …………………………………………
d. Cumulative AP Recoupment ……………………………
e. Liquidated Damages …………………………………….
f. Others ……………………………………………………..
|  | TOTAL DEDUCTION | [6 empty] | P
|  | NET AMOUNT RECEIVED | [6 empty] | P
| 4. | Balance Before this Certificate …………………………………………………………………… | [10 empty] | P | 2047366.03
| 5. | This Certificate |  | 75% Partial Billing | [8 empty] | P | 1535524.5225
|  | a. Retention (10%) …………………………………………. | [6 empty] | P | 153552.4523
|  | b. W/Holding Tax (1.786%) ……………………………………. | [7 empty] | 27420.0808
|  | c. Value Added Tax (4.464%)…………………………………… | [7 empty] | 68550.2019
d. AP Recoupment ………………………………………….
e. Liquidated Damages ……………………………………..
f. Others ……………………………………………………..
|  | TOTAL DEDUCTION …………………………………….. | [6 empty] | P | 249522.7349
|  | NET AMOUNT RECEIVED ………………………………. | [6 empty] | P | 1797843.2951
| 6. | Balance After this Certificate …………………………………………………………………….. | [10 empty] | P | 511841.5075
| Amount Due and Payable This Certificate (in words): | [6 empty] | ONE MILLION NINE HUNDRED TWWENTY NINE THOUSAND
SIX HUNDRED PESOS ONLY
Prepared by: | [5 empty] | Recommending Approval: | [5 empty] | Approved:
CHRISTOPHER B. HADSAN | [5 empty] | AGUSTIN B. GUMUWANG, Ph.D. | [5 empty] | ELLEN B. DONATO Ed.D., CESO III
DepEd Project Engineer | [5 empty] | Chief, ESSD | [6 empty] | Regional Director
ATTACHMENT:
|  |  | - | Statement of Work Accomplishment (SWA) | [9 empty] | Date
|  |  | - | Progress Photographs
-

## Abra
CERTIFICATE OF PAYMENT
| Project Name |  | : | Repair/Rehab of School Buildings in Various School Sites under the CY 2014 BEFF | [6 empty] | COP No. |  | : | 2
| Cluster No. |  | : | 4B | [6 empty] | Period Covered |  | : | Feb. 4-April 22, 2016
| School/s |  | : | Sabangan CS & Pingad NHS | [6 empty] | Remarks |  |  | Final Billing
| Contractor |  | : | Polo Engineering & Construction
CONSTRUCTION CONTRACT DATA/INFORMATION
| Original Contract Amount |  |  |  | P | 1960614.54 |  |  |  |  | Original Construction Period |  |  |  | 75 CD
| Extra Work Order Amount |  |  |  | P | [5 empty] | Addt'l Construction Period
| Revised Contract Amount |  |  |  | P | [5 empty] | Revised Construction Period
| % of Contract Paid | [9 empty] | % of Time Elapsed
| % of Work Done |  |  |  | Previous: |  | 62.65 |  | This Period: |  | 37.35% |  | To date: |  | 100%
| 1. | Total Contract Amount ………………………………………………………………………….. | [10 empty] | P | 1960614.54
| 2. | Advance Payment (AP) ……………………………………………………………………………… | [10 empty] | P
|  | a. Previous Recoupment/s ………………………………… | [6 empty] | P
|  | b. Balance of AP …………………………………………… | [6 empty] | P
| 3. | Previous Certificate/s ………………………………………………………………………………. | [10 empty] | P | 1176368.72
|  | a. Cumulative Retention ……………………………………. | [6 empty] | P | 117636.87
|  | b. Cumulative W/Holding Tax ……………………………. | [7 empty] | 21006.58
|  | c. Cumulative VAT ………………………………………… | [7 empty] | 52516.46
|  | d. Cumulative AP Recoupment …………………………… | [7 empty] | 70851.97
e. Liquidated Damages …………………………………….
f. Others ……………………………………………………..
|  | TOTAL DEDUCTION | [6 empty] | P | 262011.89
|  | NET AMOUNT RECEIVED | [6 empty] | P | 914356.83
| 4. | Balance Before this Certificate …………………………………………………………………… | [10 empty] | P | 784245.82
| 5. | This Certificate |  | Final Billing | [8 empty] | P | 784245.82
|  | a. Retention (10%) …………………………………………. | [6 empty] | P | 78424.582
|  | b. W/Holding Tax (1.786%) ……………………………………. | [7 empty] | 14004.3896
|  | c. Value Added Tax (4.464%)…………………………………… | [7 empty] | 35010.9741
|  | d. AP Recoupment …………………………………………. | [7 empty] | 47234.65
|  | e. Liquidated Damages …………………………………….. | [7 empty] | 25452.2
f. Others ……………………………………………………..
|  | TOTAL DEDUCTION …………………………………….. | [6 empty] | P | 200126.7957
|  | NET AMOUNT RECEIVED ………………………………. | [6 empty] | P | 584119.0243 | [5 empty] | 118086.621
| 6. | Balance After this Certificate …………………………………………………………………….. | [10 empty] | P | 0 |  | 47234.651
| Amount Due and Payable This Certificate (in words): | [6 empty] | FIVE HUNDRED EIGHTY FOUR THOUSAND ONE HUNDRED
NINETEEN AND 02/100 PESOS ONLY
Prepared by: | [5 empty] | Recommending Approval: | [5 empty] | Approved:
CHRISTOPHER B. HADSAN | [5 empty] | AGUSTIN B. GUMUWANG, Ph.D. | [5 empty] | ELLEN B. DONATO Ed.D., CESO III
Regional Engineer | [5 empty] | Chief, ESSD | [6 empty] | Regional Director
ATTACHMENT:
|  |  | - | Statement of Work Accomplishment (SWA) | [9 empty] | Date
|  |  | - | Progress Photographs
-