## 3A
|  |  | TIME EXTENSION No. |  | 1
Project Title : |  | Repair/Rehab of School Buildings at various Sites in CAR, Lot 3A (Ifugao Division)
Name of School: |  | Hapid National High School-Bimpal Annex
Nayon Elementary School
Hungduan National High School
Date | : | 2016-02-04
POLO ENGINEERING & CONSTRUCTION
Rm. 303 Narda's Building
Balili, La Trinidad, Benguet
In view of the Variation Order No.1(Change order) Issued , you are hereby granted a
Fifteen (15) calendar days time extension for your project.
For your guidance, the following is the status of the on-going project:
| Original Contract Period |  |  |  |  | : | 75 | CD
| Time extension granted due to change order |  |  |  |  | : | 15 | CD
| Total Contract Time including extension |  |  |  |  | : | 90 | CD
| Number of Days Used to Date |  |  |  |  | : | 72 | CD
| Number of Days Remaining |  |  |  |  | : | 23 | CD
| Original Contract Completion |  |  |  |  | : | 2016-02-06
| Revised Contract Completion Date |  |  |  |  | : | 2016-02-21
Please acknowledge receipt of this order by dating, signing and returning three
(3) copies. The fourth copy is for your file.
Prepared by: |  |  |  | Recommending Approval:
|  | CHRISTOPHER B. HADSAN |  |  |  |  | AGUSTIN B. GUMUWANG Ph.D.
|  | Regional Engineer |  |  |  |  | CHIEF-ESSD
APPROVED:
ELLEN B. DONATO Ed.D., CESO III
Regional Director
I HEREBY ACKNOWLEDGE receipt of this Order.
POLO ENGINEERING & CONSTRUCTION
by: MARK M. POLO
Date:

## 3b
|  |  | TIME EXTENSION No. |  | 1
Project Title : |  | Repair/Rehab of School Buildings at various Sites in CAR, Lot 4B (Mountain Province Division)
Name of School: |  | Bontoc CS
Date | : | 2016-02-24
POLO ENGINEERING & CONSTRUCTION
Rm. 303 Narda's Building
Balili, La Trinidad, Benguet
In view of the Variation Order No.1 (Change order) issued, you are hereby granted a
Fifteen (15) Calendar days time extension for your project.
For your guidance, the following is the status of the on-going project:
| Original Contract Period |  |  |  |  | : | 90 | CD
| Time extension granted due to variation order |  |  |  |  | : | 15 | CD
| Total Contract Time including extension |  |  |  |  | : | 105 | CD
| Number of Days Used to Date |  |  |  |  | : | 85 | CD
| Number of Days Remaining |  |  |  |  | : | 20 | CD
| Original Contract Completion |  |  |  |  | : | 2016-02-29
| Revised Contract Completion Date |  |  |  |  | : | 2016-03-15
Please acknowledge receipt of this order by dating, signing and returning three
(3) copies. The fourth copy is for your file.
Prepared by: |  |  |  | Recommending Approval:
|  | CHRISTOPHER B. HADSAN |  |  |  |  | AGUSTIN B. GUMUWANG Ph.D.
|  | Regional Engineer |  |  |  |  | CHIEF-ESSD
APPROVED:
ELLEN B. DONATO Ed.D., CESO III
Regional Director
I HEREBY ACKNOWLEDGE receipt of this Order.
POLO ENGINEERING & CONSTRUCTION
by: MARK M. POLO
Date: