## ES-Sumag
EVALUATION SHEET
Package |  |  | : | CY 2011
Project Title |  |  | : | Construction of Kindergarten School Building at Kabugao Central School,
Kabugao, Apayao; Pedro Bunot CS, Poblacion, Calanasan, Apayao; Southern Conner
CS, Buluan, Luna, Apayao
Location |  |  | : | Apayao Division
Contractor |  |  | : | Sumag Builders Construction
Subject |  |  | : | Time Extension
I. | CONTRACT DATA
| Contract Amount |  |  |  | : | 1. PHP 825,334.74 - Kabugao CS
2. PHP 826,208.87 - Pedro Bunot CS
3. PHP 811,215.87 - Southern Conner CS
| Date of Mobilization/Project Started |  |  |  | : | 2012-08-08
| Contract Duration |  |  |  | : | 60 C.D. |  |  |  | jun | 30
| Original Contract Expiry Date |  |  |  | : | 2012-10-08 |  |  |  | july | 31 | 29
Approved Contract Time Extension no. 1 due to
|  | minimal possession of site granted |  |  | : | 20 C.D.
Revised Contract Expiry Date due to
|  | minimal possession of site granted |  |  | : | 2012-10-28
II. | SUMMARY OF EVALUATION OF CONTRACT TIME SUSPENSION
| A. | Justification
The Contract Time Extension is in view of the consideration to the letter request of the contractor.
His request is due to the minimal possession of site granted to the Contractor by the School due to lack of classrooms
| B. | Evaluated Contract Time Suspension
Breakdown of Contract Time Extension :
|  | Due to continuous heavy rains and typhoons that hit the area |  |  |  |  | 20 C.D.
20 C.D.
Prepared by:
Engr. CULLEN S. WEGIYON
PFSEU
|  | Recommending Approval: |  |  |  |  | Approved:
|  | VENANCIO P. BALOS |  |  |  |  | ELLEN B. DONATO, Ed. D. CESO III
|  | RPFC, PFSEU |  |  |  |  | Director IV
Conforme:
___________________
Sumag Builders Construction
( siganture over printed name)
______________________
Date
[7 empty] | april 29 | 2
[7 empty] | may 31 | 31 | 9
[7 empty] | jun 30 | 30 | 30
[7 empty] | july | 31 | 31
[7 empty] | Aug | 31 | 20
[8 empty] | 125 | 90

## TAR-Sumag
long bond
CONTRACT TIME ADJUSTMENT REQUEST
Request No. 1
I. | CONTRACT DATA
| Cluster |  |  |  |  | : |  | CY 2011
| Project Title |  |  |  |  | : | Construction of Kindergarten School Building at Kabugao Central School,
Kabugao, Apayao; Pedro Bunot CS, Poblacion, Calanasan, Apayao; Southern Conner
CS, Buluan, Luna, Apayao
| Location |  |  |  |  | : | Apayao Division
| Contractor |  |  |  |  | : | Sumag Builders Construction
| Contract Amount |  |  |  |  | : | 1. PHP 825,334.74 - Kabugao CS
2. PHP 826,208.87 - Pedro Bunot CS
3. PHP 811,215.87 - Southern Conner CS
II. | NATURE OF REQUEST
| Requesting Party |  |  |  |  | : |  | Sumag Builders Construction |  |  |  | Requested No. of Days |  |  |  | : | 20 C.D.
|  | A. | Due to Non-payment | [8 empty] | X | B. | Due to Bad Weather Condition/Other
conditons
|  |  | Billing No. | [5 empty] | : |  |  |  |  | Required Supporting Papers |  |  |  | :
|  |  | Date of Confirmation of SWA | [5 empty] | :
|  |  | Gross Amount | [5 empty] | : | [5 empty] | Approved Construction Schedule
Construction Logbook
Weather Chart
|  |  | Required Supproting Papers | [5 empty] | : | [5 empty] | Certificate from PAGASA, if necessary
[14 empty] | X | Contractor's Project Engineer Report
|  |  |  | Copy of LDDAP | [10 empty] | Certified by DepEd Project Engineer and Noted
|  |  |  | Copy of Official Receipt | [10 empty] | by the Owner
|  |  |  | Copy of Confirmation of SWA | [10 empty] | Progress Photos/Site Photos
|  | C. | Others
|  |  | Reasons |  | :
(Please see attached letter request for contract time extension of contractor.)
|  |  | Required Supproting Papers | [5 empty] | : | (As required by the Owner)
III. | APPROVAL
| Engineer's Evaluation | [5 empty] | : | 20 C.D. |  |  | Recommendation |  |  |  |  | : | Time suspension
[11 empty] | Recommended No. of Days : | [5 empty] | 20 C.D.
| Evaluated No. of Days | [5 empty] | : | 20 C.D. |  |  | Revised Completion Date |  |  |  |  | : | October 28, 2012
| Evaluated by: | [12 empty] | Recommended by:
| Engr. CULLEN S. WEGIYON | [12 empty] | VENANCIO P. BALOS
| PFSEU | [12 empty] | RPFC, PFSEU
| Conforme: | [12 empty] | Approved by:
| Sumag Builders Construction | [12 empty] | ELLEN B. DONATO,Ed.D., CESO III
| Contractor | [12 empty] | Director IV
Attachments |  |  |  | :
1. | Contractor's Letter Request
2. | Engineer's Evaluation Sheet
3. | Other Necessary Supporting Documents

## TAR-Jotcresm
long bond
CONTRACT TIME ADJUSTMENT REQUEST
Request No. 1
I. | CONTRACT DATA
| Cluster |  |  |  |  | : |  | CY 2011
| Project Title |  |  |  |  | : | Repair and Rehabilitation of Kindergarten School Building at Baguio Central School
| Location |  |  |  |  | : | Kayang Extension, Baguio City
| Contractor |  |  |  |  | : | Jotcresm Engineering and Enterprises
| Contract Amount |  |  |  |  | : | PHP 568,937.32
II. | NATURE OF REQUEST
| Requesting Party |  |  |  |  | : |  | Jotcresm Engineering and Enterprises |  |  |  | Requested No. of Days |  |  |  | : | 25 C.D.
|  | A. | Due to Non-payment | [9 empty] | B. | Due to Bad Weather Condition/Other
conditons
|  |  | Billing No. | [5 empty] | : |  |  |  |  | Required Supporting Papers |  |  |  | :
|  |  | Date of Confirmation of SWA | [5 empty] | :
|  |  | Gross Amount | [5 empty] | : | [5 empty] | Approved Construction Schedule
Construction Logbook
Weather Chart
|  |  | Required Supproting Papers | [5 empty] | : | [5 empty] | Certificate from PAGASA, if necessary
Contractor's Project Engineer Report
|  |  |  | Copy of LDDAP | [10 empty] | Certified by DepEd Project Engineer and Noted
|  |  |  | Copy of Official Receipt | [10 empty] | by the Owner
|  |  |  | Copy of Confirmation of SWA | [10 empty] | Progress Photos/Site Photos
| X | C. | Others
|  |  | Reasons |  | : | Minimal possession of site granted to the Contractor by the School due to lack of classrooms
as referred to the Special Conditions of Contract
(Please see attached letter request for contract time extension of contractor.)
|  |  | Required Supproting Papers | [5 empty] | : | (As required by the Owner)
III. | APPROVAL
| Engineer's Evaluation | [5 empty] | : | 25 C.D. |  |  | Recommendation |  |  |  |  | : | Time suspension
[11 empty] | Recommended No. of Days : | [5 empty] | 25 C.D.
| Evaluated No. of Days | [5 empty] | : | 25 C.D. |  |  | Revised Completion Date |  |  |  |  | : | October 20, 2012
| Evaluated by: | [12 empty] | Recommended by:
| Engr. CULLEN S. WEGIYON | [12 empty] | VENANCIO P. BALOS
| PFSEU | [12 empty] | RPFC, PFSEU
| Conforme: | [12 empty] | Approved by:
| Jotcresm Engineering and Enterprises | [12 empty] | ELLEN B. DONATO,Ed.D., CESO III
| Contractor | [12 empty] | Director IV
Attachments |  |  |  | :
1. | Contractor's Letter Request
2. | Engineer's Evaluation Sheet
3. | Other Necessary Supporting Documents

## ES-Jotcresm
EVALUATION SHEET
Package |  |  | : | CY 2011
Project Title |  |  | : | REPAIR AND REHABILITATION OF KINDERGARTEN BUILDING AT BAGUIO CENTRAL SCHOOL
Location |  |  | : | Kayang Extension, Baguio City
Contractor |  |  | : | Jotcresm Engineering and Enterprises
Subject |  |  | : | Time Extension
I. | CONTRACT DATA
| Contract Amount |  |  |  | : | PHP 568,937.32
| Date of Mobilization/Project Started |  |  |  | : | 2012-07-27
| Contract Duration |  |  |  | : | 60 C.D. |  |  |  | jun | 30
| Original Contract Expiry Date |  |  |  | : | 2012-09-25 |  |  |  | july | 31 | 29
Approved Contract Time Extension no. 1 due to
|  | minimal possession of site granted |  |  | : | 25 C.D.
Revised Contract Expiry Date due to
|  | minimal possession of site granted |  |  | : | 2012-10-20
II. | SUMMARY OF EVALUATION OF CONTRACT TIME SUSPENSION
| A. | Justification
The Contract Time Extension is in view of the consideration to the letter request of the contractor.
His request is due to the minimal possession of site granted to the Contractor by the School due to lack of classrooms
| B. | Evaluated Contract Time Suspension
Breakdown of Contract Time Extension :
|  | Due to continuous heavy rains and typhoons that hit the area |  |  |  |  | 25 C.D.
25 C.D.
Prepared by:
Engr. CULLEN S. WEGIYON
PFSEU
|  | Recommending Approval: |  |  |  |  | Approved:
|  | VENANCIO P. BALOS |  |  |  |  | ELLEN B. DONATO, Ed. D. CESO III
|  | RPFC, PFSEU |  |  |  |  | Director IV
Conforme:
___________________
Jotcresm Engineering and Enterprises
( siganture over printed name)
______________________
Date
[7 empty] | april 29 | 2
[7 empty] | may 31 | 31 | 9
[7 empty] | jun 30 | 30 | 30
[7 empty] | july | 31 | 31
[7 empty] | Aug | 31 | 20
[8 empty] | 125 | 90

## ES-ET Amilig
EVALUATION SHEET
Package |  |  | : | CY 2011
Project Title |  |  | : | CONSTRUCTION OF 1-STY,1-CLRM PRESCHOOL/KINDERGARTEN SCHOOL BUILDING W/TOILET
Location |  |  | : | Balbalasang Elementary School, Balbalan, Kalinga
Contractor |  |  | : | ET Amilig Construction
Subject |  |  | : | Time Suspension
I. | CONTRACT DATA
| Contract Amount |  |  |  | : | Php 780,589.49
| Date of Mobilization/Project Started |  |  |  | : | 2012-07-23
| Contract Duration |  |  |  | : | 60 C.D. |  |  |  | jun | 30
| Original Contract Expiry Date |  |  |  | : | 2012-09-21 |  |  |  | july | 31 | 29
Approved Contract Time Extension no. 1 due to
|  | unworkable bad weather condition |  |  | : | 20 C.D.
Revised Contract Expiry Date due to
|  | bad weather condition |  |  | : | 2012-10-11
II. | SUMMARY OF EVALUATION OF CONTRACT TIME SUSPENSION
| A. | Justification
The Contract Time Extension is in view of the consideration to the letter request of the contractor.
His request is due to bad weather condition, non-stop heavy rains and typhoon Gener, typhoon Igme and
Habagat that hit the province, which causes heavy rainfull. (Typhoon Gener, Typoon Helen, Typhoon Igme and
Habagat for the month of July and August).
| B. | Evaluated Contract Time Suspension
Breakdown of Contract Time Extension :
|  | Due to continuous heavy rains and typhoons that hit the area |  |  |  |  | 20 C.D.
20 C.D.
Prepared by:
Engr. CULLEN S. WEGIYON
PFSEU
|  | Recommending Approval: |  |  |  |  | Approved:
|  | VENANCIO P. BALOS |  |  |  |  | ELLEN B. DONATO, Ed. D. CESO III
|  | RPFC, PFSEU |  |  |  |  | Director IV
Conforme:
___________________
ET Amilig Construction
( siganture over printed name)
______________________
Date
[7 empty] | april 29 | 2
[7 empty] | may 31 | 31 | 9
[7 empty] | jun 30 | 30 | 30
[7 empty] | july | 31 | 31
[7 empty] | Aug | 31 | 20
[8 empty] | 125 | 90

## TAR-ETAmilig
long bond
CONTRACT TIME ADJUSTMENT REQUEST
Request No. 1
I. | CONTRACT DATA
| Cluster |  |  |  |  | : |  | CY 2011
| Project Title |  |  |  |  | : | Construction of One Story, One Classroom Kindergarten School Building w/ Toilet
| Location |  |  |  |  | : | Balbalasang Elementary School, Balbalan, Kalinga
| Contractor |  |  |  |  | : | ET Amilig Construction
| Contract Amount |  |  |  |  | : | Php 780,589.49
II. | NATURE OF REQUEST
| Requesting Party |  |  |  |  | : |  | ET Amilig Construction |  |  |  | Requested No. of Days |  |  |  | : | 30 C.D.
|  | A. | Due to Non-payment | [8 empty] | X | B. | Due to Bad Weather Condition/Other
conditons
|  |  | Billing No. | [5 empty] | : |  |  |  |  | Required Supporting Papers |  |  |  | :
|  |  | Date of Confirmation of SWA | [5 empty] | :
|  |  | Gross Amount | [5 empty] | : | [5 empty] | Approved Construction Schedule
Construction Logbook
[14 empty] | X | Weather Chart
|  |  | Required Supproting Papers | [5 empty] | : |  |  |  |  | X | Certificate from PAGASA, if necessary
[14 empty] | X | Contractor's Project Engineer Report
|  |  |  | Copy of LDDAP | [10 empty] | Certified by DepEd Project Engineer and Noted
|  |  |  | Copy of Official Receipt | [10 empty] | by the Owner
|  |  |  | Copy of Confirmation of SWA | [9 empty] | X | Progress Photos/Site Photos
|  | C. | Others
|  |  | Reasons |  | : | More ground levelling/widening of construction area need to be done to met the required
measurement and area for the school building project.
(Please see attached letter request for contract time suspension of contractor.)
|  |  | Required Supproting Papers | [5 empty] | : | (As required by the Owner)
III. | APPROVAL
| Engineer's Evaluation | [5 empty] | : | 20 C.D. |  |  | Recommendation |  |  |  |  | : | Time suspension
[11 empty] | Recommended No. of Days : | [5 empty] | 20 C.D.
| Evaluated No. of Days | [5 empty] | : | 20 C.D. |  |  | Revised Completion Date |  |  |  |  | : | October 11, 2012
| Evaluated by: | [12 empty] | Recommended by:
| Engr. CULLEN S. WEGIYON | [12 empty] | VENANCIO P. BALOS
| PFSEU | [12 empty] | RPFC, PFSEU
| Conforme: | [12 empty] | Approved by:
| ET Amilig Construction | [12 empty] | ELLEN B. DONATO,Ed.D., CESO III
| Contractor | [12 empty] | Director IV
Attachments |  |  |  | :
1. | Contractor's Letter Request
2. | Engineer's Evaluation Sheet
3. | Other Necessary Supporting Documents

## TAR-KVC
long bond
CONTRACT TIME ADJUSTMENT REQUEST
Request No. 1
I. | CONTRACT DATA
| Cluster |  |  |  |  | : |  | CY 2011
| Project Title |  |  |  |  | : | Construction of One Story, One Classroom Kindergarten School Building w/ Toilet
| Location |  |  |  |  | : | 1. Ampusongan Elementary School, Bakun, Benguet
2. Pinto Elementary School, Alfonso Lista, Ifugao
| Contractor |  |  |  |  | : | KVC Construction
| Contract Amount |  |  |  |  | : | 1. Ampusongan ES - Php. 768,984.50
2. Pinto ES - Php. 783,901.64
II. | NATURE OF REQUEST
| Requesting Party |  |  |  |  | : |  | KVC Construction |  |  |  | Requested No. of Days |  |  |  | : | 20 C.D.
|  | A. | Due to Non-payment | [8 empty] | X | B. | Due to Bad Weather Condition/Other
conditons
|  |  | Billing No. | [5 empty] | : |  |  |  |  | Required Supporting Papers |  |  |  | :
|  |  | Date of Confirmation of SWA | [5 empty] | :
|  |  | Gross Amount | [5 empty] | : | [5 empty] | Approved Construction Schedule
Construction Logbook
[14 empty] | X | Weather Chart
|  |  | Required Supproting Papers | [5 empty] | : |  |  |  |  | X | Certificate from PAGASA, if necessary
[14 empty] | X | Contractor's Project Engineer Report
|  |  |  | Copy of LDDAP | [10 empty] | Certified by DepEd Project Engineer and Noted
|  |  |  | Copy of Official Receipt | [10 empty] | by the Owner
|  |  |  | Copy of Confirmation of SWA | [10 empty] | Progress Photos/Site Photos
|  | C. | Others
|  |  | Reasons |  | : | More ground levelling/widening of construction area need to be done to met the required
measurement and area for the school building project.
(Please see attached letter request for contract time suspension of contractor.)
|  |  | Required Supproting Papers | [5 empty] | : | (As required by the Owner)
III. | APPROVAL
| Engineer's Evaluation | [5 empty] | : | 20 C.D. |  |  | Recommendation |  |  |  |  | : | Time suspension
[11 empty] | Recommended No. of Days : | [5 empty] | 20 C.D.
| Evaluated No. of Days | [5 empty] | : | 20 C.D. |  |  | Revised Completion Date |  |  |  |  | : | October 11, 2012
| Evaluated by: | [12 empty] | Recommended by:
| Engr. CULLEN S. WEGIYON | [12 empty] | VENANCIO P. BALOS
| PFSEU | [12 empty] | RPFC, PFSEU
| Conforme: | [12 empty] | Approved by:
| KVC Construction | [12 empty] | ELLEN B. DONATO,Ed.D., CESO III
| Contractor | [12 empty] | Director IV
Attachments |  |  |  | :
1. | Contractor's Letter Request
2. | Engineer's Evaluation Sheet
3. | Other Necessary Supporting Documents

## ES-KVC
EVALUATION SHEET
Package |  |  | : | CY 2011
Project Title |  |  | : | CONSTRUCTION OF 1-STY,1-CLRM PRESCHOOL/KINDERGARTEN SCHOOL BUILDING W/TOILET
Location |  |  | : | 1. Ampusongan Elementary School, Bakun, Benguet
2. Pinto Elementary School, Alfonso Lista, Ifugao
Contractor |  |  | : | KVC Construction
Subject |  |  | : | Time Suspension
I. | CONTRACT DATA
| Contract Amount |  |  |  | : | 1. Ampusongan ES - Php. 768,984.50
2. Pinto ES - Php. 783,901.64
| Date of Mobilization/Project Started |  |  |  | : | 2012-07-23
| Contract Duration |  |  |  | : | 60 C.D. |  |  |  | jun | 30
| Original Contract Expiry Date |  |  |  | : | 2012-09-21 |  |  |  | july | 31 | 29
Approved Contract Time Extension no. 1 due to
|  | unworkable bad weather condition |  |  | : | 20 C.D.
Revised Contract Expiry Date due to
|  | bad weather condition |  |  | : | 2012-10-11
II. | SUMMARY OF EVALUATION OF CONTRACT TIME SUSPENSION
| A. | Justification
The Contract Time Extension is in view of the consideration to the letter request of the contractor.
His request is due to bad weather condition, non-stop heavy rains and typhoon Gener, typhoon Igme and
Habagat that hit the province, which causes heavy rainfull. (Typhoon Gener, Typoon Helen, Typhoon Igme and
Habagat for the month of July and August).
| B. | Evaluated Contract Time Suspension
Breakdown of Contract Time Extension :
|  | Due to continuous heavy rains and typhoons that hit the area |  |  |  |  | 20 C.D.
20 C.D.
Prepared by:
Engr. CULLEN S. WEGIYON
PFSEU
|  | Recommending Approval: |  |  |  |  | Approved:
|  | VENANCIO P. BALOS |  |  |  |  | ELLEN B. DONATO, Ed. D. CESO III
|  | RPFC, PFSEU |  |  |  |  | Director IV
Conforme:
___________________
KVC Construction
( siganture over printed name)
______________________
Date
[7 empty] | april 29 | 2
[7 empty] | may 31 | 31 | 9
[7 empty] | jun 30 | 30 | 30
[7 empty] | july | 31 | 31
[7 empty] | Aug | 31 | 20
[8 empty] | 125 | 90

## TAR-HGW=3
long bond
CONTRACT TIME ADJUSTMENT REQUEST
Request No. 1
I. | CONTRACT DATA
| Cluster |  |  |  |  | : |  | CY 2011
| Project Title |  |  |  |  | : | Repair and Rehabilitation of Building 1,2,3 & Guard House
| Location |  |  |  |  | : | DepED-CAR Regional Office, Wangal, La Trinidad, Benguet
| Contractor |  |  |  |  | : | HGW=3 Engineering & Construction
| Contract Amount |  |  |  |  | : | Php 916,186.96
II. | NATURE OF REQUEST
| Requesting Party |  |  |  |  | : |  | HGW=3 Engineering & Construction |  |  |  | Requested No. of Days |  |  |  | : | 25 C.D.
|  | A. | Due to Non-payment | [8 empty] | X | B. | Due to Bad Weather Condition/Other
conditons
|  |  | Billing No. | [5 empty] | : |  |  |  |  | Required Supporting Papers |  |  |  | :
|  |  | Date of Confirmation of SWA | [5 empty] | :
|  |  | Gross Amount | [5 empty] | : | [5 empty] | Approved Construction Schedule
Construction Logbook
[14 empty] | X | Weather Chart
|  |  | Required Supproting Papers | [5 empty] | : |  |  |  |  | X | Certificate from PAGASA, if necessary
[14 empty] | X | Contractor's Project Engineer Report
|  |  |  | Copy of LDDAP | [10 empty] | Certified by DepEd Project Engineer and Noted
|  |  |  | Copy of Official Receipt | [10 empty] | by the Owner
|  |  |  | Copy of Confirmation of SWA | [10 empty] | Progress Photos/Site Photos
|  | C. | Others
|  |  | Reasons |  | : | More ground levelling/widening of construction area need to be done to met the required
measurement and area for the school building project.
(Please see attached letter request for contract time suspension of contractor.)
|  |  | Required Supproting Papers | [5 empty] | : | (As required by the Owner)
III. | APPROVAL
| Engineer's Evaluation | [5 empty] | : | 20 C.D. |  |  | Recommendation |  |  |  |  | : | Time suspension
[11 empty] | Recommended No. of Days : | [5 empty] | 20 C.D.
| Evaluated No. of Days | [5 empty] | : | 20 C.D. |  |  | Revised Completion Date |  |  |  |  | : | October 13, 2012
| Evaluated by: | [12 empty] | Recommended by:
| Engr. CULLEN S. WEGIYON | [12 empty] | VENANCIO P. BALOS
| PFSEU | [12 empty] | RPFC, PFSEU
| Conforme: | [12 empty] | Approved by:
| HGW=3 Engineering & Construction | [12 empty] | ELLEN B. DONATO,Ed.D., CESOIII
| Contractor | [12 empty] | Director IV
Attachments |  |  |  | :
1. | Contractor's Letter Request
2. | Engineer's Evaluation Sheet
3. | Other Necessary Supporting Documents

## ES-HGW=3
EVALUATION SHEET
Package |  |  | : | CY 2011
Project Title |  |  | : | Repair & Rehabilitation of Building 1,2,3 & Guard House
Location |  |  | : | DepeD-CAR Regional Office, Wangal, La Trinidad, Benguet
Contractor |  |  | : | HGW=3 Engineering & Construction
Subject |  |  | : | Time Suspension
I. | CONTRACT DATA
| Contract Amount |  |  |  | : | Php 916,186.96
| Date of Mobilization/Project Started |  |  |  | : | 2012-07-25
| Contract Duration |  |  |  | : | 60 C.D. |  |  |  | jun | 30
| Original Contract Expiry Date |  |  |  | : | 2012-08-25 |  |  |  | july | 31 | 29
Approved Contract Time Extension no. 1 due to
|  | unworkable bad weather condition |  |  | : | 20 C.D.
Revised Contract Expiry Date due to
|  | bad weather condition |  |  | : | 2012-10-13
II. | SUMMARY OF EVALUATION OF CONTRACT TIME SUSPENSION
| A. | Justification
The Contract Time Extension is in view of the consideration to the letter request of the contractor.
His request is due to bad weather condition, non-stop heavy rains and typhoon Gener, typhoon Igme and
Habagat that hit the province, which causes heavy rainfull. (Typhoon Gener, Typoon Helen, Typhoon Igme and
Habagat for the month of July and August).
| B. | Evaluated Contract Time Suspension
Breakdown of Contract Time Extension :
|  | Due to continuous heavy rains and typhoons that hit the area |  |  |  |  | 20 C.D.
20 C.D.
Prepared by:
Engr. CULLEN S. WEGIYON
PFSEU
|  | Recommending Approval: |  |  |  |  | Approved:
|  | VENANCIO P. BALOS |  |  |  |  | ELLEN B. DONATO, Ed. D. CESO III
|  | RPFC, PFSEU |  |  |  |  | Director IV
Conforme:
___________________
HGW=3 Engineering & Construction
( siganture over printed name)
______________________
Date
[7 empty] | april 29 | 2
[7 empty] | may 31 | 31 | 9
[7 empty] | jun 30 | 30 | 30
[7 empty] | july | 31 | 31
[7 empty] | Aug | 31 | 20
[8 empty] | 125 | 90

## TAR-LabGenEngr
long bond
CONTRACT TIME ADJUSTMENT REQUEST
Request No. 1
I. | CONTRACT DATA
| Cluster |  |  |  |  | : |  | CY 2011
| Project Title |  |  |  |  | : | Construction of One Story, One Classroom Kindergarten School Building w/ Toilet
| Location |  |  |  |  | : | Loo Elementary School, Buguias, Benguet
| Contractor |  |  |  |  | : | LAB General Engineering
| Contract Amount |  |  |  |  | : | Php 772,907.38
II. | NATURE OF REQUEST
| Requesting Party |  |  |  |  | : |  | LAB General Engineering |  |  |  | Requested No. of Days |  |  |  | : | 25 C.D.
|  | A. | Due to Non-payment | [8 empty] | X | B. | Due to Bad Weather Condition/Other
conditons
|  |  | Billing No. | [5 empty] | : |  |  |  |  | Required Supporting Papers |  |  |  | :
|  |  | Date of Confirmation of SWA | [5 empty] | :
|  |  | Gross Amount | [5 empty] | : | [5 empty] | Approved Construction Schedule
Construction Logbook
[14 empty] | X | Weather Chart
|  |  | Required Supproting Papers | [5 empty] | : | [5 empty] | Certificate from PAGASA, if necessary
[14 empty] | X | Contractor's Project Engineer Report
|  |  |  | Copy of LDDAP | [10 empty] | Certified by DepEd Project Engineer and Noted
|  |  |  | Copy of Official Receipt | [10 empty] | by the Owner
|  |  |  | Copy of Confirmation of SWA | [9 empty] | X | Progress Photos/Site Photos
|  | C. | Others
|  |  | Reasons |  | : | More ground levelling/widening of construction area need to be done to met the required
measurement and area for the school building project.
(Please see attached letter request for contract time suspension of contractor.)
|  |  | Required Supproting Papers | [5 empty] | : | (As required by the Owner)
III. | APPROVAL
| Engineer's Evaluation | [5 empty] | : | 25 C.D. |  |  | Recommendation |  |  |  |  | : | Time suspension
[11 empty] | Recommended No. of Days : | [5 empty] | 25 C.D.
| Evaluated No. of Days | [5 empty] | : | 25 C.D. |  |  | Revised Completion Date |  |  |  |  | : | October 17, 2012
| Evaluated by: | [12 empty] | Recommended by:
| Engr. CULLEN S. WEGIYON | [12 empty] | VENANCIO P. BALOS
| PFSEU | [12 empty] | RPFC, PFSEU
| Conforme: | [12 empty] | Approved by:
| LAB General Engineering | [12 empty] | ELLEN B. DONATO,Ed.D., CESOIII
| Contractor | [12 empty] | Director IV
Attachments |  |  |  | :
1. | Contractor's Letter Request
2. | Engineer's Evaluation Sheet
3. | Other Necessary Supporting Documents

## ES-LabGenEngr
EVALUATION SHEET
Package |  |  | : | CY 2011
Project Title |  |  | : | CONSTRUCTION OF 1-STY,1-CLRM PRESCHOOL/KINDERGARTEN SCHOOL BUILDING W/TOILET
Location |  |  | : | Loo Elementary School, Buguias, Benguet
Contractor |  |  | : | LAB General Engineering
Subject |  |  | : | Time Suspension
I. | CONTRACT DATA
| Contract Amount |  |  |  | : | Php 772,907.38
| Date of Mobilization/Project Started |  |  |  | : | 2012-07-25
| Contract Duration |  |  |  | : | 60 C.D. |  |  |  | jun | 30
| Original Contract Expiry Date |  |  |  | : | 2012-09-22 |  |  |  | july | 31 | 29
Approved Contract Time Extension no. 1 due to
|  | unworkable bad weather condition |  |  | : | 25 C.D.
Revised Contract Expiry Date due to
|  | bad weather condition |  |  | : | 2012-10-17
II. | SUMMARY OF EVALUATION OF CONTRACT TIME SUSPENSION
| A. | Justification
The Contract Time Extension is in view of the consideration to the letter request of the contractor.
His request is due to bad weather condition, non-stop heavy rains and typhoon Gener, typhoon Igme and
Habagat that hit the province, which causes heavy rainfull. (Typhoon Gener, Typoon Helen, Typhoon Igme and
Habagat for the month of July and August).
| B. | Evaluated Contract Time Suspension
Breakdown of Contract Time Extension :
|  | Due to continuous heavy rains and typhoons that hit the area |  |  |  |  | 25 c.d.
25 c.d.
Prepared by:
Engr. CULLEN S. WEGIYON
PFSEU
|  | Recommending Approval: |  |  |  |  | Approved:
|  | VENANCIO P. BALOS |  |  |  |  | ELLEN B. DONATO, Ed. D. CESO III
|  | RPFC, PFSEU |  |  |  |  | Director IV
Conforme:
___________________
LAB General Engineering
( siganture over printed name)
______________________
Date
[7 empty] | april 29 | 2
[7 empty] | may 31 | 31 | 9
[7 empty] | jun 30 | 30 | 30
[7 empty] | july | 31 | 31
[7 empty] | Aug | 31 | 20
[8 empty] | 125 | 90

## TAR-BontocBuilders2
long bond
CONTRACT TIME ADJUSTMENT REQUEST
Request No. 1
I. | CONTRACT DATA
| Cluster |  |  |  |  | : |  | CY 2011
| Project Title |  |  |  |  | : | Construction of One Story, One Classroom Kindergarten SCHOOL building w/ Toilet
| Location |  |  |  |  | : | Tapapan Elementary School and Bauko Central School, Bauko, Mt. Province
| Contractor |  |  |  |  | : | Bontoc Builders
| Contract Amount |  |  |  |  | : | Php 639,855.52 - Tapapan Elementary School
Php 644,531.84 - Bauko Central School
II. | NATURE OF REQUEST
| Requesting Party |  |  |  |  | : |  | Bontoc Builders |  |  |  | Requested No. of Days |  |  |  | :
|  | A. | Due to Non-payment | [8 empty] | X | B. | Due to Bad Weather Condition/Other
conditons
|  |  | Billing No. | [5 empty] | : |  |  |  |  | Required Supporting Papers |  |  |  | :
|  |  | Date of Confirmation of SWA | [5 empty] | :
|  |  | Gross Amount | [5 empty] | : | [5 empty] | Approved Construction Schedule
[14 empty] | X | Construction Logbook
[14 empty] | X | Weather Chart
|  |  | Required Supproting Papers | [5 empty] | : |  |  |  |  | X | Certificate from PAGASA, if necessary
Contractor's Project Engineer Report
|  |  |  | Copy of LDDAP | [10 empty] | Certified by DepEd Project Engineer and Noted
|  |  |  | Copy of Official Receipt | [10 empty] | by the Owner
|  |  |  | Copy of Confirmation of SWA | [10 empty] | Progress Photos
|  | C. | Others
|  |  | Reasons |  | : | Due to bad weather condition, continuous heavy rains experienced during the past few weeks
has greatly hampered the construction activities.
(Please see attached letter request for contract time suspension of contractor.)
|  |  | Required Supproting Papers | [5 empty] | : | (As required by the Owner)
III. | APPROVAL
| Engineer's Evaluation | [5 empty] | : | 25 C.D. |  |  | Recommendation |  |  |  |  | : | Time suspension
[11 empty] | Recommended No. of Days : | [5 empty] | 25 C.D.
| Evaluated No. of Days | [5 empty] | : | 25 C.D. |  |  | Revised Completion Date |  |  |  |  | : | October 19, 2012
| Evaluated by: | [12 empty] | Recommended by:
| FERNANDO A. SEMANERO, JR | [12 empty] | VENANCIO P. BALOS
| Regional Lead Engineer, PFSED | [12 empty] | RPFC, PFSEU
| Conforme: | [12 empty] | Approved by:
| BONTOC BUILDERS | [12 empty] | ELLEN B. DONATO,Ed.D., CESOIII
| Contractor | [12 empty] | Director IV
Attachments |  |  |  | :
1. | Contractor's Letter Request
2. | Engineer's Evaluation Sheet
3. | Other Necessary Supporting Documents

## ES-BontocBuilders2
EVALUATION SHEET
Package |  |  | : | CY 2011
Project Title |  |  | : | CONSTRUCTION OF 1-STY,1-CLRM PRESCHOOL/KINDERGARTEN SCHOOL BUILDING W/TOILET
Location |  |  | : | 1.Tapapan Elementary School, Bauko, Mt. Province
2. Bauko Central School, Bauko, Mt. Province
Contractor |  |  | : | Bontoc Builders
Subject |  |  | : | Time Suspension
I. | CONTRACT DATA
| Contract Amount |  |  |  | : | Php 639,855.52 - Tapapan Elementary School
Php 644,531.84 - Bauko Central School
| Date of Mobilization/Project Started |  |  |  | : | 2012-07-27
| Contract Duration |  |  |  | : | 60 C.D. |  |  |  | jun | 30
| Original Contract Expiry Date |  |  |  | : | 2012-09-24 |  |  |  | july | 31 | 29
Approved Contract Time Extension no. 1 due to
|  | unworkable bad weather condition |  |  | : | 25 C.D.
Revised Contract Expiry Date due to
|  | bad weather condition |  |  | : | 2012-10-19
II. | SUMMARY OF EVALUATION OF CONTRACT TIME SUSPENSION
| A. | Justification
The Contract Time Extension is in view of the consideration to the letter request of the contractor.
His request is due to bad weather condition, non-stop heavy rains and typhoon Gener, typhoon Igme and
Habagat that hit the province, which causes heavy rainfull. (Typhoon Gener, Typoon Helen, Typhoon Igme and
Habagat for the month of July and August).
| B. | Evaluated Contract Time Suspension
Breakdown of Contract Time Extension :
|  | Due to continuous heavy rains and typhoons that hit the area |  |  |  |  | 25 c.d.
25 c.d.
Prepared by:
FERNANDO A. SEMANERO, JR
Regional Lead Engineer, PFSED
|  | Recommending Approval: |  |  |  |  | Approved:
|  | VENANCIO P. BALOS |  |  |  |  | ELLEN B. DONATO, Ed. D. CESO III
|  | RPFC, PFSEU |  |  |  |  | Director IV
Conforme:
___________________
BONTOC BUILDERS
( siganture over printed name)
______________________
Date
[7 empty] | april 29 | 2
[7 empty] | may 31 | 31 | 9
[7 empty] | jun 30 | 30 | 30
[7 empty] | july | 31 | 31
[7 empty] | Aug | 31 | 20
[8 empty] | 125 | 90

## TAR-BontocBuilders1
long bond
CONTRACT TIME ADJUSTMENT REQUEST
Request No. 1
I. | CONTRACT DATA
| Cluster |  |  |  |  | : |  | CY 2011
| Project Title |  |  |  |  | : | Construction of One Story, One Classroom Kindergarten SCHOOL building w/ Toilet
| Location |  |  |  |  | : | Guina-ang Elementary School, Bontoc, Mountain Province
| Contractor |  |  |  |  | : | Bontoc Builders
| Contract Amount |  |  |  |  | : | Php 669,128.76
II. | NATURE OF REQUEST
| Requesting Party |  |  |  |  | : |  | Bontoc Builders |  |  |  | Requested No. of Days |  |  |  | :
|  | A. | Due to Non-payment | [8 empty] | X | B. | Due to Bad Weather Condition/Other
conditons
|  |  | Billing No. | [5 empty] | : |  |  |  |  | Required Supporting Papers |  |  |  | :
|  |  | Date of Confirmation of SWA | [5 empty] | :
|  |  | Gross Amount | [5 empty] | : | [5 empty] | Approved Construction Schedule
Construction Logbook
Weather Chart
|  |  | Required Supproting Papers | [5 empty] | : | [5 empty] | Certificate from PAGASA, if necessary
[14 empty] | X | Contractor's Project Engineer Report
|  |  |  | Copy of LDDAP | [10 empty] | Certified by DepEd Project Engineer and Noted
|  |  |  | Copy of Official Receipt | [10 empty] | by the Owner
|  |  |  | Copy of Confirmation of SWA | [10 empty] | Progress Photos/Site Photos
| X | C. | Others
|  |  | Reasons |  | : | More ground levelling/widening of construction area need to be done to met the required
measurement and area for the school building project.
(Please see attached letter request for contract time suspension of contractor.)
|  |  | Required Supproting Papers | [5 empty] | : | (As required by the Owner)
III. | APPROVAL
| Engineer's Evaluation | [5 empty] | : | 25 C.D. |  |  | Recommendation |  |  |  |  | : | Time suspension
[11 empty] | Recommended No. of Days : | [5 empty] | 25 C.D.
| Evaluated No. of Days | [5 empty] | : | 25 C.D. |  |  | Revised Completion Date |  |  |  |  | : | October 19, 2012
| Evaluated by: | [12 empty] | Recommended by:
| FERNANDO A. SEMANERO, JR | [12 empty] | VENANCIO P. BALOS
| Regional Lead Engineer, PFSED | [12 empty] | RPFC, PFSEU
| Conforme: | [12 empty] | Approved by:
| BONTOC BUILDERS | [12 empty] | ELLEN B. DONATO,Ed.D., CESOIII
| Contractor | [12 empty] | Director IV
Attachments |  |  |  | :
1. | Contractor's Letter Request
2. | Engineer's Evaluation Sheet
3. | Other Necessary Supporting Documents

## ES-BontocBuilders1
EVALUATION SHEET
Package |  |  | : | CY 2011
Project Title |  |  | : | CONSTRUCTION OF 1-STY,1-CLRM PRESCHOOL/KINDERGARTEN SCHOOL BUILDING W/TOILET
Location |  |  | : | Guina-ang Elementary School, Bontoc, Mountain Province
Contractor |  |  | : | Bontoc Builders
Subject |  |  | : | Time Suspension
I. | CONTRACT DATA
| Contract Amount |  |  |  | : | Php 792,366.22
| Date of Mobilization/Project Started |  |  |  | : | 2012-07-27
| Contract Duration |  |  |  | : | 60 C.D. |  |  |  | jun | 30
| Original Contract Expiry Date |  |  |  | : | 2012-09-24 |  |  |  | july | 31 | 29
Approved Contract Time Extension no. 1 due to
|  | excavation/widening of construction area |  |  | : | 25 C.D.
Revised Contract Expiry Date due to
|  | contract time extension no. 1 |  |  | : | 2012-10-19
II. | SUMMARY OF EVALUATION OF CONTRACT TIME SUSPENSION
| A. | Justification
The Contract Time Extension is in view of the consideration to the letter request of the contractor.
His request is due to more ground levelling to widen the area so that the required area for
the school building will be met.
| B. | Evaluated Contract Time Suspension
Breakdown of Contract Time Extension :
|  | Due to more ground leveling to widen area needs |  |  |  |  | 25 c.d.
25 c.d.
Prepared by:
FERNANDO A. SEMANERO, JR
Regional Lead Engineer, PFSED
|  | Recommending Approval: |  |  |  |  | Approved:
|  | VENANCIO P. BALOS |  |  |  |  | ELLEN B. DONATO, Ed. D. CESO III
|  | RPFC, PFSEU |  |  |  |  | Director IV
Conforme:
___________________
BONTOC BUILDERS
(siganture over printed name)
______________________
Date
[7 empty] | april 29 | 2
[7 empty] | may 31 | 31 | 9
[7 empty] | jun 30 | 30 | 30
[7 empty] | july | 31 | 31
[7 empty] | Aug | 31 | 20
[8 empty] | 125 | 90

## TAR-Begal
long bond
CONTRACT TIME ADJUSTMENT REQUEST
Request No. 1
I. | CONTRACT DATA
| Cluster |  |  |  |  | : |  | CY 2011
| Project Title |  |  |  |  | : | Construction of One Story, One Classroom Kindergarten SCHOOL building w/ Toilet
| Location |  |  |  |  | : | 1. Gumhang Elementary School, Tinoc, Ifugao
2. Wangwang Elementary School, Tinoc, Ifugao
3. Lagawe Central School, Lagawe, Ifugao
| Contractor |  |  |  |  | : | Begal Design and Construction
| Contract Amount |  |  |  |  | : | Php 792,366.22 - Gumhang Elementary School
Php 792,366.22 - Wangwang Elementary School
Php 791,225.36 - Lagawe Central School
II. | NATURE OF REQUEST
| Requesting Party |  |  |  |  | : | Begal Design and Construction |  |  |  |  | Requested No. of Days |  |  |  | : | 30 c.d.
|  | A. | Due to Non-payment | [8 empty] | X | B. | Due to Bad Weather Condition/Other
conditons
|  |  | Billing No. | [5 empty] | : |  |  |  |  | Required Supporting Papers |  |  |  | :
|  |  | Date of Confirmation of SWA | [5 empty] | :
|  |  | Gross Amount | [5 empty] | : | [5 empty] | Approved Construction Schedule
Construction Logbook
[14 empty] | X | Weather Chart
|  |  | Required Supproting Papers | [5 empty] | : |  |  |  |  | X | Certificate from PAGASA, if necessary
Contractor's Project Engineer Report
|  |  |  | Copy of LDDAP | [10 empty] | Certified by DepEd Project Engineer and Noted
|  |  |  | Copy of Official Receipt | [10 empty] | by the Owner
|  |  |  | Copy of Confirmation of SWA | [10 empty] | Progress Photos
|  | C. | Others
|  |  | Reasons |  | : | Due to bad weather condition, continuous heavy rains and inaccessibility of roads
going to project site caused by landslide and road widening.
(Please see attached letter request for contract time suspension of contractor.)
|  |  | Required Supproting Papers | [5 empty] | : | (As required by the Owner)
III. | APPROVAL
| Engineer's Evaluation | [5 empty] | : | 25 C.D. |  |  | Recommendation |  |  |  |  | : | Time suspension
[11 empty] | Recommended No. of Days : | [5 empty] | 25 C.D.
| Evaluated No. of Days | [5 empty] | : | 25 C.D. |  |  | Revised Completion Date |  |  |  |  | : | October 15, 2012
| Evaluated by: | [12 empty] | Recommended by:
| FERNANDO A. SEMANERO, JR | [12 empty] | VENANCIO P. BALOS
| Regional Lead Engineer, PFSED | [12 empty] | RPFC, PFSEU
| Conforme: | [12 empty] | Approved by:
| BEGAL DESIGN AND CONSTRUCTION | [12 empty] | ELLEN B. DONATO,Ed.D., CESOIII
| Contractor | [12 empty] | Director IV
Attachments |  |  |  | :
1. | Contractor's Letter Request
2. | Engineer's Evaluation Sheet
3. | Other Necessary Supporting Documents

## ES-Begal
EVALUATION SHEET
Package |  |  | : | CY 2011
Project Title |  |  | : | CONSTRUCTION OF 1-STY,1-CLRM PRESCHOOL/KINDERGARTEN SCHOOL BUILDING W/TOILET
Location |  |  | : | 1. Gumhang Elementary School, Tinoc, Ifugao
2. Wangwang Elementary School, Tinoc, Ifugao
3. Lagawe Central School, Lagawe, Ifugao
Contractor |  |  | : | Begal Design and Construction
Subject |  |  | : | Time Suspension
I. | CONTRACT DATA
| Contract Amount |  |  |  | : | Php 792,366.22 - Gumhang Elementary School
Php 792,366.22 - Wangwang Elementary School
Php 791,225.36 - Lagawe Central School
| Date of Mobilization/Project Started |  |  |  | : | 2012-07-23
| Contract Duration |  |  |  | : | 60 C.D. |  |  |  |  | 30
| Original Contract Expiry Date |  |  |  | : | 2012-09-20 |  |  |  | july | 31 | 29
Approved Contract Time Extension no. 1 due to
|  | unworkable bad weather condition |  |  | : | 25 C.D.
Revised Contract Expiry Date due to
|  | Contract time extension no. 1 |  |  | : | October 15, 2012
II. | SUMMARY OF EVALUATION OF CONTRACT TIME SUSPENSION
| A. | Justification
The Contract Time Extension is in view of the consideration to the letter request of the contractor.
His request is due to bad weather condition and typhoon Gener, typhoon Igme and Habagat that hit the province ,
which causes heavy rainfull. (Typhoon Gener, Typoon Helen, Typhoon Igme and Habagat for the
month of July and August).
| B. | Evaluated Contract Time Suspension
Breakdown of Contract Time Extension :
|  | Due to continuous heavy rains and typhoons that hit the area |  |  |  |  | 25 C.D.
25 C.D.
Prepared by:
FERNANDO SEMANERO
PFSED Project Engineer
|  | Recommending Approval: |  |  |  |  | Approved:
|  | VENANCIO P. BALOS |  |  |  |  | ELLEN B. DONATO, Ed. D. CESO III
|  | RPFC, PFSEU |  |  |  |  | Director IV
Conforme:
___________________
BEGAL DESIGN AND CONSTRUCTION
( siganture over printed name)
______________________
Date
[7 empty] | april 29 | 2
[7 empty] | may 31 | 31 | 9
[7 empty] | jun 30 | 30 | 30
[7 empty] | july | 31 | 31
[7 empty] | Aug | 31 | 20
[8 empty] | 125 | 90

## ES-WWW.construction
EVALUATION SHEET
Package |  |  | : | CY 2011
Project Title |  |  | : | CONSTRUCTION OF 1-STY,1-CLRM PRESCHOOL/KINDERGARTEN SCHOOL BUILDING W/TOILET
Location |  |  | : | Mayoyao Central school, Mayoyao, Ifugao and Bagtangan Elementary School, Bakun, Benguet
Contractor |  |  | : | WWW. Construction
Subject |  |  | : | Time Suspension
I. | CONTRACT DATA
| Contract Amount |  |  |  | : | Php 786,857.33 - Mayoyao Central School
Php 745,443.79 - Bagtangan Elementary School
| Date of Mobilization/Project Started |  |  |  | : | 2012-07-24
| Contract Duration |  |  |  | : | 60c.d. |  |  |  | jun | 30
| Original Contract Expiry Date |  |  |  | : | 2012-09-21 |  |  |  | july | 31 | 29
Approved Contract Time Extension no. 1 due to
|  | unworkable bad weather condition |  |  | : | 25 C.D.
Revised Contract Expiry Date due to
|  | contract time extension no. 1 |  |  | : | October 16, 2012
II. | SUMMARY OF EVALUATION OF CONTRACT TIME SUSPENSION
| A. | Justification
The Contract Time Extension is in view of the consideration to the letter request of the contractor.
His request is due to bad weather condition and typhoon Gener, typhoon Igme and Habagat that hit the province ,
which causes heavy rainfull. (Typhoon Gener, Typoon Helen, Typhoon Igme and Habagat for the
month of July and August).
| B. | Evaluated Contract Time Suspension
Breakdown of Contract Time Extension :
|  | Due to continuous heavy rains and typhoons that hit the area |  |  |  |  | 25 C.D.
25 C.D.
Prepared by:
FERNANDO A. SEMANERO, JR
Regional Lead Engineer, PFSED
|  | Recommending Approval: |  |  |  |  | Approved:
|  | VENANCIO P. BALOS |  |  |  |  | ELLEN B. DONATO, Ed. D. CESO III
|  | RPFC, PFSEU |  |  |  |  | Director IV
Conforme:
___________________
WWW.CONSTRUCTION
( siganture over printed name)
______________________
Date
[7 empty] | april 29 | 2
[7 empty] | may 31 | 31 | 9
[7 empty] | jun 30 | 30 | 30
[7 empty] | july | 31 | 31
[7 empty] | Aug | 31 | 20
[8 empty] | 125 | 90

## TAR-WWW.construction
long bond
CONTRACT TIME ADJUSTMENT REQUEST
Request No. 1
I. | CONTRACT DATA
| Cluster |  |  |  |  | : |  | CY 2011
| Project Title |  |  |  |  | : | Construction of One Story, One Classroom Kindergarten SCHOOL building w/ Toilet
| Location |  |  |  |  | : | Mayoyao Central school, Mayoyao, Ifugao and Bagtangan Elementary School, Bakun, Benguet
| Contractor |  |  |  |  | : | WWW. Construction
| Contract Amount |  |  |  |  | : | Mayoyao CS - Php 786,875.33
[6 empty] | : | Bagtangan ES - Php 745,443.79
II. | NATURE OF REQUEST
| Requesting Party |  |  |  |  | : |  | WWW.Construction |  |  |  | Requested No. of Days |  |  |  | :
|  | A. | Due to Non-payment | [8 empty] | X | B. | Due to Bad Weather Condition/Other
conditons
|  |  | Billing No. | [5 empty] | : |  |  |  |  | Required Supporting Papers |  |  |  | :
|  |  | Date of Confirmation of SWA | [5 empty] | :
|  |  | Gross Amount | [5 empty] | : | [5 empty] | Approved Construction Schedule
Construction Logbook
[14 empty] | X | Weather Chart
|  |  | Required Supproting Papers | [5 empty] | : |  |  |  |  | X | Certificate from PAGASA, if necessary
Contractor's Project Engineer Report
|  |  |  | Copy of LDDAP | [10 empty] | Certified by DepEd Project Engineer and Noted
|  |  |  | Copy of Official Receipt | [10 empty] | by the Owner
|  |  |  | Copy of Confirmation of SWA | [10 empty] | Progress Photos
|  | C. | Others
|  |  | Reasons |  | : | Due to bad weather condition, continuous heavy rains and inaccessibility of roads
going to project site caused by landslide and road widening.
(Please see attached letter request for contract time suspension of contractor.)
|  |  | Required Supproting Papers | [5 empty] | : | (As required by the Owner)
III. | APPROVAL
| Engineer's Evaluation | [5 empty] | : | 25 C.D. |  |  | Recommendation |  |  |  |  | : | Time suspension
[11 empty] | Recommended No. of Days : | [5 empty] | 25 C.D.
| Evaluated No. of Days | [5 empty] | : | 25 C.D. |  |  | Revised Completion Date |  |  |  |  | : | October 16, 2012
| Evaluated by: | [12 empty] | Recommended by:
| FERNANDO A. SEMANERO, JR | [12 empty] | VENANCIO P. BALOS
| PFSED, Regional Lead Engineer | [12 empty] | RPFC, PFSEU
| Conforme: | [12 empty] | Approved by:
| WWW.Construction | [12 empty] | ELLEN B. DONATO,Ed.D., CESOIII
| Contractor | [12 empty] | Director IV
Attachments |  |  |  | :
1. | Contractor's Letter Request
2. | Engineer's Evaluation Sheet
3. | Other Necessary Supporting Documents

## csd-tar
long bond
CONTRACT TIME ADJUSTMENT REQUEST
Request No. 1
I. | CONTRACT DATA
| Cluster |  |  |  |  | : |  | CY 2011
| Project Title |  |  |  |  | : | Construction of Kindergarten School Building at Rizal Central School
Babalag East, Rizal, Kalinga
| Location |  |  |  |  | : | Kalinga Division
| Contractor |  |  |  |  | : | CSD Engineering and Construction
| Contract Amount |  |  |  |  | : | PHP 745,347.03
II. | NATURE OF REQUEST
| Requesting Party |  |  |  |  | : |  | CSD Engineering and Construction |  |  |  | Requested No. of Days |  |  |  | : | 15 C.D.
|  | A. | Due to Non-payment | [8 empty] | X | B. | Due to Bad Weather Condition/Other
conditons
|  |  | Billing No. | [5 empty] | : |  |  |  |  | Required Supporting Papers |  |  |  | :
|  |  | Date of Confirmation of SWA | [5 empty] | :
|  |  | Gross Amount | [5 empty] | : | [5 empty] | Approved Construction Schedule
Construction Logbook
[14 empty] | x | Weather Chart
|  |  | Required Supproting Papers | [5 empty] | : |  |  |  |  | x | Certificate from PAGASA, if necessary
[14 empty] | X | Contractor's Project Engineer Report
|  |  |  | Copy of LDDAP | [10 empty] | Certified by DepEd Project Engineer and Noted
|  |  |  | Copy of Official Receipt | [10 empty] | by the Owner
|  |  |  | Copy of Confirmation of SWA | [10 empty] | Progress Photos/Site Photos
|  | C. | Others
|  |  | Reasons |  | :
(Please see attached letter request for contract time extension of contractor.)
|  |  | Required Supproting Papers | [5 empty] | : | (As required by the Owner)
III. | APPROVAL
| Engineer's Evaluation | [5 empty] | : | 15 C.D. |  |  | Recommendation |  |  |  |  | : | Time suspension
[11 empty] | Recommended No. of Days : | [5 empty] | 15 C.D.
| Evaluated No. of Days | [5 empty] | : | 15 C.D. |  |  | Revised Completion Date |  |  |  |  | : | October 6, 2012
| Evaluated by: | [12 empty] | Recommended by:
| Engr. CULLEN S. WEGIYON | [12 empty] | VENANCIO P. BALOS
| Regional Engineer Designate,PFSEU | [12 empty] | RPFC, PFSEU
| Conforme: | [12 empty] | Approved by:
| CSD Engineering and Construction | [12 empty] | ELLEN B. DONATO,Ed.D., CESO III
| Contractor | [12 empty] | Director IV
Attachments |  |  |  | :
1. | Contractor's Letter Request
2. | Engineer's Evaluation Sheet
3. | Other Necessary Supporting Documents

## csd-es
EVALUATION SHEET
Package |  |  | : | CY 2011
Project Title |  |  | : | CONSTRUCTION OF 1-STY,1-CLRM PRESCHOOL/KINDERGARTEN SCHOOL BUILDING W/TOILET
Location |  |  | : | Rizal Central School, Babalag East, Rizal, Kalinga
Contractor |  |  | : | CSD Engineering and Construction
Subject |  |  | : | Time Extension
I. | CONTRACT DATA
| Contract Amount |  |  |  | : | Php 745,347.03
| Date of Mobilization/Project Started |  |  |  | : | 2012-07-24
| Contract Duration |  |  |  | : | 60c.d. |  |  |  | jun | 30
| Original Contract Expiry Date |  |  |  | : | September 22, 2012 |  |  |  | july | 31 | 29
Approved Contract Time Extension no. 1 due to
|  | unworkable bad weather condition |  |  | : | 15 C.D.
Revised Contract Expiry Date due to
|  | contract time extension no. 1 |  |  | : | October 6, 2012
II. | SUMMARY OF EVALUATION OF CONTRACT TIME SUSPENSION
| A. | Justification
The Contract Time Extension is in view of the consideration to the letter request of the contractor.
His request is due to bad weather condition and typhoon Gener, typhoon Igme and Habagat that hit the province ,
which causes heavy rainfull. (Typhoon Gener, Typoon Helen, Typhoon Igme and Habagat for the
month of July and October).
| B. | Evaluated Contract Time Extension:
Breakdown of Contract Time Extension :
|  | Due to continuous heavy rains and typhoons that hit the area |  |  |  |  | 15 C.D.
15 C.D.
Prepared by:
Cullen S. Wegiyon
Regional Engineer Designate, PFSEU
|  | Recommending Approval: |  |  |  |  | Approved:
|  | VENANCIO P. BALOS |  |  |  |  | ELLEN B. DONATO, Ed. D. CESO III
|  | RPFC, PFSEU |  |  |  |  | Director IV
Conforme:
___________________
CSD Engineering and Construction
( siganture over printed name)
______________________
Date
[7 empty] | april 29 | 2
[7 empty] | may 31 | 31 | 9
[7 empty] | jun 30 | 30 | 30
[7 empty] | july | 31 | 31
[7 empty] | Aug | 31 | 20
[8 empty] | 125 | 90

## Sheet1
Republic of the Philippines
Department of Education
Division of Baguio City
82 Military Cut-off, Baguio City
CONTRACT TIME ADJUSTMENT REQUEST
Request No. 1
I. | CONTRACT DATA
| Cluster |  |  |  |  | : |  |  |  | CY 2011 PRESCHOOL/KINDERGARTEN SCHOOL BUILDING PROGRAM
| Project Title |  |  |  |  | : | Construction of 1-STY,1-CLRM PRESCHOOL/KINDERGARTEN SCHOOL BUILDING W/ TOILET
| Location |  |  |  |  | : | TAPAPAN, BAUKO, MOUNTAIN PROVINCE
| Contractor |  |  |  |  | : | BONTOC BUILDERS
| Contract Amount |  |  |  |  | : | Php
II. | NATURE OF REQUEST
| Requesting Party |  |  |  |  | : |  | BONTOC BUILDERS |  |  |  | Requested No. of Days |  |  |  | : | 25
|  | A. | Due to Non-payment | [8 empty] | X | B. | Due to Bad Weather Condition
|  |  | Billing No. | [5 empty] | : |  |  |  |  | Required Supporting Papers |  |  |  | :
|  |  | Date of Confirmation of SWA | [5 empty] | :
|  |  | Gross Amount | [5 empty] | : | [5 empty] | Approved Construction Schedule
Construction Logbook
Weather Chart
|  |  | Required Supproting Papers | [5 empty] | : |  |  |  |  | X | Certificate from PAGASA, if necessary
Contractor's Project Engineer Report
|  |  |  | Copy of LDDAP | [10 empty] | Certified by DepEd Project Engineer and Noted
|  |  |  | Copy of Official Receipt | [10 empty] | by the Owner
|  |  |  | Copy of Confirmation of SWA | [10 empty] | Progress Photos
|  | C. | Others
|  |  | Reasons |  | :
(Please see attached letter request for contract time suspension of contractor.)
|  |  | Required Supproting Papers | [5 empty] | : | (As required by the Owner)
III. | APPROVAL
| Engineer's Evaluation | [5 empty] | : |  |  |  | Recommendation |  |  |  |  | : | Time suspension
[11 empty] | Recommended No. of Days : | [5 empty] | 20 c.d.
| Evaluated No. of Days | [5 empty] | : | 20 c.d. |  |  | Revised Completion Date |  |  |  |  | :
| Evaluated by: | [12 empty] | Recommended by:
|  | FERNANDO SEMANERO | [11 empty] | VENANCIO P. BALOS
| PFSED, Project Engineer | [12 empty] | RPFC,PFSEU
| Conforme: | [12 empty] | Approved by:
|  |  | BONTOC BUILDERS/REPRESENTATIVE | [10 empty] | ELLEN B. DONATO,Ed.D., CESO III
| Contractor | [12 empty] | Director IV
Attachments |  |  |  | :
1. | Contractor's Letter Request
2. | Engineer's Evaluation Sheet
3. | Other Necessary Supporting Documents

## Sheet2
EVALUATION SHEET
Package |  |  | : | CY 2011 PRESCHOOL/KINDERGARTEN SCHOOL BUILDING PROJECT
Project Title |  |  | : | CONSTRUCTION OF 1-STY,1-CLRM SCHOOL BUILDING W/ TOILET
Location |  |  | :
Contractor |  |  | :
Subject |  |  | : | Time Suspension
I. | CONTRACT DATA
| Contract Amount |  |  |  | : | Php
| Date of Mobilization/Project Started |  |  |  | :
| Contract Duration |  |  |  | : |  |  |  | jun | 30
| Original Contract Expiry Date |  |  |  | : |  |  |  | july | 31 | 29
| Approved Contract Time Extension due to |  |  |  | :
|  | bad weather condition |  |  | :
Revised Contract Expiry Date due to
|  | bad weather condition |  |  | :
II. | SUMMARY OF EVALUATION OF CONTRACT TIME SUSPENSION
| A. | Justification
The Contract Time Extension is in view of the consideration to the letter request of the contractor.
His request is due to bad weather condition and typhoons that hit the province , which causes heavy rainfull.
| B. | Evaluated Contract Time Suspension
Breakdown of Contract Time Extension :
|  | Due to continnous heavy rains and typhoons that hit the area |  |  |  |  | 20 c.d.
20 c.d.
Prepared by:
FERNANDO SEMANERO
PFSED Project Engineer
|  | Recommending Approval: |  |  |  |  | Approved:
|  | VENANCIO P. BALOS |  |  |  |  | ELLEN B. DONATO,Ed.D., CESO III
|  | RPFC, PFSEU |  |  |  |  | Director IV
Conforme:
___________________
BONTOC BUILDERS
( siganture over printed name)
______________________
Date
9
30
31
20
90

## pert-cpm
Package | [5 empty] | : | CY 2011 PRESCHOOL/KINDERGARTEN SCHOOL BUILDING PROJECT
Project Title | [5 empty] | : | CONSTRUCTION OF 1-STY,1CLRM BUILDING W/ TOILET
School | [5 empty] | : | GUINA-ANG Elementary School
Location | [5 empty] | : | Guina-ang, Bontoc, Mt. Province
Division | [5 empty] | : | Mountain Province
PERT-CPM
C A L E N D A R D A Y S
| 0 | 5 |  |  | 10 |  |  |  | 15 |  | 20 |  | 25 |  | 30 |  | 35 |  | 40 |  | 45 | 50 |  | 55 | 60 | 65 | 70 | 75
B
|  |  |  | A | [5 empty] | C | [9 empty] | F | [8 empty] | H
E
[16 empty] | D | [6 empty] | G
ACTIVITIES :
|  | A | = | Mobilization and Temporary Facilities | [7 empty] | E | = | Plumbing Works
|  | B | = | Hauling of Materials | [7 empty] | F | = | Architectural
|  | C | = | Sub-Structures | [7 empty] | G | = | Electrical Works
|  | D | = | Superstructure | [7 empty] | H | = | Demobilization
Prepared by:
VMR Construction
Contractor
1
1
1
2
1
1
4
1
1
5
5
1
55
7
1
1
3
1
1
8
8
1
1
6
7
1
1

## Sheet3
CONTRACT TIME ADJUSTMENT REQUEST
Request No. 1
I. | CONTRACT DATA
| Cluster |  |  |  |  | : |  | CY 2011
| Project Title |  |  |  |  | : | Construction of One Story, One Classroom Kindergarten SCHOOL building w/ Toilet
| Location |  |  |  |  | : | Guina-ang Elementary School
| Contractor |  |  |  |  | : | Bontoc Builders
| Contract Amount |  |  |  |  | : | Php
II. | NATURE OF REQUEST
| Requesting Party |  |  |  |  | : |  | LAB General Engineering |  |  |  | Requested No. of Days |  |  |  | :
|  | A. | Due to Non-payment | [8 empty] | X | B. | Due to Bad Weather Condition
|  |  | Billing No. | [5 empty] | : |  |  |  |  | Required Supporting Papers |  |  |  | :
|  |  | Date of Confirmation of SWA | [5 empty] | :
|  |  | Gross Amount | [5 empty] | : | [5 empty] | Approved Construction Schedule
[14 empty] | X | Construction Logbook
Weather Chart
|  |  | Required Supproting Papers | [5 empty] | : | [5 empty] | Certificate from PAGASA, if necessary
Contractor's Project Engineer Report
|  |  |  | Copy of LDDAP | [10 empty] | Certified by DepEd Project Engineer and Noted
|  |  |  | Copy of Official Receipt | [10 empty] | by the Owner
|  |  |  | Copy of Confirmation of SWA | [10 empty] | Progress Photos
|  | C. | Others
|  |  | Reasons |  | : | More ground levelling/widening of construction area need to be done to met the required measure-
ment and area for the school building project.
(Please see attached letter request for contract time suspension of contractor.)
|  |  | Required Supproting Papers | [5 empty] | : | (As required by the Owner)
III. | APPROVAL
| Engineer's Evaluation | [5 empty] | : |  |  |  | Recommendation |  |  |  |  | : | Time suspension
[11 empty] | Recommended No. of Days : | [5 empty] | 25 c.d.
| Evaluated No. of Days | [5 empty] | : | 25 c.d. |  |  | Revised Completion Date |  |  |  |  | :
| Evaluated by: | [12 empty] | Recommended by:
| FERNANDO SEMANERO | [13 empty] | VENANCIO P. BALOS
| PFSED, Project Engineer | [13 empty] | RPFC, PFSEU
| Conforme: | [12 empty] | Approved by:
|  |  | BONTOC BUILDERS | [10 empty] | ELLEN B. DONATO,Ed.D., CESOIII
| Contractor | [13 empty] | Director IV
Attachments |  |  |  | :
1. | Contractor's Letter Request
2. | Engineer's Evaluation Sheet
3. | Other Necessary Supporting Documents