## TAR-WWW.construction
long bond
CONTRACT TIME ADJUSTMENT REQUEST
Request No. 2
I. | CONTRACT DATA
| Cluster |  |  |  |  | : |  | CY 2011
| Project Title |  |  |  |  | : | Construction of One Story, One Classroom Kindergarten SCHOOL building w/ Toilet
| Location |  |  |  |  | : | Mayoyao Central School, Mayoyao, Ifugao
| Contractor |  |  |  |  | : | WWW. Construction
| Contract Amount |  |  |  |  | : | Mayoyao CS - Php 786,875.33
II. | NATURE OF REQUEST
| Requesting Party |  |  |  |  | : |  | WWW.Construction |  |  |  | Requested No. of Days |  |  |  | :
|  | A. | Due to Non-payment | [8 empty] | X | B. | Due to Bad Weather Condition/Other
conditons
|  |  | Billing No. | [5 empty] | : |  |  |  |  | Required Supporting Papers |  |  |  | :
|  |  | Date of Confirmation of SWA | [5 empty] | :
|  |  | Gross Amount | [5 empty] | : | [5 empty] | Approved Construction Schedule
Construction Logbook
Weather Chart
|  |  | Required Supproting Papers | [5 empty] | : | [5 empty] | Certificate from PAGASA, if necessary
[14 empty] | X | Contractor's Project Engineer Report
|  |  |  | Copy of LDDAP | [10 empty] | Certified by DepEd Project Engineer and Noted
|  |  |  | Copy of Official Receipt | [10 empty] | by the Owner
|  |  |  | Copy of Confirmation of SWA | [10 empty] | Progress Photos
|  | C. | Others
|  |  | Reasons |  | : | Due to bad weather condition/continuous rainfall brought by the recent Typhoons Marcy and
Nina that caused project delay.
(Please see attached letter request for contract time suspension of contractor.)
|  |  | Required Supproting Papers | [5 empty] | : | (As required by the Owner)
III. | APPROVAL
| Engineer's Evaluation | [5 empty] | : | 25 C.D. |  |  | Recommendation |  |  |  |  | : | Time suspension
[11 empty] | Recommended No. of Days : | [5 empty] | 20 C.D.
| Evaluated No. of Days | [5 empty] | : | 20 C.D. |  |  | Revised Completion Date |  |  |  |  | : | November 5, 2012
| Evaluated by: | [12 empty] | Recommended by:
| FERNANDO A. SEMANERO, JR | [12 empty] | VENANCIO P. BALOS
| PFSED, Regional Lead Engineer | [12 empty] | RPFC, PFSEU
| Conforme: | [12 empty] | Approved by:
| WWW.Construction | [12 empty] | ELLEN B. DONATO,Ed.D., CESOIII
| Contractor | [12 empty] | Director IV
Attachments |  |  |  | :
1. | Contractor's Letter Request
2. | Engineer's Evaluation Sheet
3. | Other Necessary Supporting Documents

## ES-WWW.construction
EVALUATION SHEET
Package |  |  | : | CY 2011
Project Title |  |  | : | CONSTRUCTION OF 1-STY,1-CLRM PRESCHOOL/KINDERGARTEN SCHOOL BUILDING W/TOILET
Location |  |  | : | Mayoyao Central school, Mayoyao, Ifugao
Contractor |  |  | : | WWW. Construction
Subject |  |  | : | Secondary Time Suspension/Extension
I. | CONTRACT DATA
| Contract Amount |  |  |  | : | Php 786,857.33 - Mayoyao Central School
| Date of Mobilization/Project Started |  |  |  | : | 2012-07-24
| Contract Duration |  |  |  | : | 60 C.D. |  |  |  | jun | 30
| Original Contract Expiry Date |  |  |  | : | 2012-09-21 | (October 16, 2012 - 1st Approved) |  |  | july | 31 | 29
Approved Contract Time Extension no. 2 due to
|  | unworkable bad weather condition |  |  | : | 20 C.D.
Revised Contract Expiry Date due to
|  | contract time extension no. 2 |  |  | : | November 5, 2012
II. | SUMMARY OF EVALUATION OF CONTRACT TIME SUSPENSION
| A. | Justification
The Contract Time Extension is in view of the consideration to the letter request of the contractor.
His request is due to bad weather condition/continuous rainfall brought by the recent Typhoons Marcy and
Nina that caused project delay.
| B. | Evaluated Contract Time Suspension
Breakdown of Contract Time Extension :
|  | Due to continuous heavy rains and typhoons that hit the area |  |  |  |  | 20 C.D.
20 C.D.
Prepared by:
FERNANDO A. SEMANERO, JR
Regional Lead Engineer, PFSED
|  | Recommending Approval: |  |  |  |  | Approved:
|  | VENANCIO P. BALOS |  |  |  |  | ELLEN B. DONATO, Ed. D. CESO III
|  | RPFC, PFSEU |  |  |  |  | Director IV
Conforme:
___________________
WWW.CONSTRUCTION
( siganture over printed name)
______________________
Date
[7 empty] | april 29 | 2
[7 empty] | may 31 | 31 | 9
[7 empty] | jun 30 | 30 | 30
[7 empty] | july | 31 | 31
[7 empty] | Aug | 31 | 20
[8 empty] | 125 | 90

## PreschoolTAR-HGW=3
long bond
CONTRACT TIME ADJUSTMENT REQUEST
Request No. 1 | Request No. 2
I. | CONTRACT DATA
| Cluster |  |  |  |  | : |  | CY 2011
| Project Title |  |  |  |  | : | Construction of Kindergarten School Building at Bulo East Elementary School
| Location |  |  |  |  | : | Eastern Tabuk, Kalinga
| Contractor |  |  |  |  | : | HGW=3 Engineering & Construction
| Contract Amount |  |  |  |  | : | Php 779,919.07
II. | NATURE OF REQUEST
| Requesting Party |  |  |  |  | : |  | HGW=3 Engineering & Construction |  |  |  | Requested No. of Days |  |  |  | : | 20 C.D.
|  | A. | Due to Non-payment | [9 empty] | B. | Due to Bad Weather Condition/Other
conditons
|  |  | Billing No. | [5 empty] | : |  |  |  |  | Required Supporting Papers |  |  |  | :
|  |  | Date of Confirmation of SWA | [5 empty] | :
|  |  | Gross Amount | [5 empty] | : | [5 empty] | Approved Construction Schedule
Construction Logbook
Weather Chart
|  |  | Required Supproting Papers | [5 empty] | : | [5 empty] | Certificate from PAGASA, if necessary
Contractor's Project Engineer Report
|  |  |  | Copy of LDDAP | [10 empty] | Certified by DepEd Project Engineer and Noted
|  |  |  | Copy of Official Receipt | [10 empty] | by the Owner
|  |  |  | Copy of Confirmation of SWA | [10 empty] | Progress Photos/Site Photos
| X | C. | Others
|  |  | Reasons |  | : | Due to material-procurement problems on the suppliers end/part (suppliers' factory breakdown).
(Please see attached letter request for contract time suspension of contractor.)
|  |  | Required Supproting Papers | [5 empty] | : | (As required by the Owner)
III. | APPROVAL
| Engineer's Evaluation | [5 empty] | : | 20 C.D. |  |  | Recommendation |  |  |  |  | : | Time suspension
[11 empty] | Recommended No. of Days : | [5 empty] | 20 C.D.
| Evaluated No. of Days | [5 empty] | : | 20 C.D. |  |  | Revised Completion Date |  |  |  |  | : | November 2, 2012
| Evaluated by: | [12 empty] | Recommended by:
| FERNANDO A. SEMANERO, JR | [12 empty] | VENANCIO P. BALOS
| Regional Lead Engineer, PFSED | [12 empty] | RPFC, PFSEU
| Conforme: | [12 empty] | Approved by:
| HGW=3 Engineering & Construction | [12 empty] | ELLEN B. DONATO,Ed.D., CESOIII
| Contractor | [12 empty] | Director IV
Attachments |  |  |  | :
1. | Contractor's Letter Request
2. | Engineer's Evaluation Sheet
3. | Other Necessary Supporting Documents

## PreschoolES-HGW=3
EVALUATION SHEET
Package |  |  | : | CY 2011
Project Title |  |  | : | Construction of Kindergarten School Building at Bulo East Elementary School
Location |  |  | : | Eastern Tabuk, Kalinga
Contractor |  |  | : | HGW=3 Engineering & Construction
Subject |  |  | : | Secondary Time Extension
I. | CONTRACT DATA
| Contract Amount |  |  |  | : | Php 779,919.07
| Date of Mobilization/Project Started |  |  |  | : | 2012-07-25
| Contract Duration |  |  |  | : | 60 C.D. |  |  |  | jun | 30
| Original Contract Expiry Date |  |  |  | : | 2012-10-05 |  |  |  | july | 31 | 29
Approved Contract Time Extension no. 1 due to
|  | material-procurement problems |  |  | : | 20 C.D.
Revised Contract Expiry Date due to
|  | material-procurement problems |  |  | : | 2012-11-02
II. | SUMMARY OF EVALUATION OF CONTRACT TIME SUSPENSION
| A. | Justification
The Contract Time Extension is in view of the consideration to the letter request of the contractor.
His request is due to material-procurement problems on the suppliers end/part (suppliers' factory breakdown).
| B. | Evaluated Contract Time Suspension
Breakdown of Contract Time Extension :
|  | Due to limited source/fabrication of materials |  |  |  |  | 20 C.D.
20 C.D.
Prepared by:
FERNANDO A. SEMANERO, JR
Regional Lead Engineer, PFSED
|  | Recommending Approval: |  |  |  |  | Approved:
|  | VENANCIO P. BALOS |  |  |  |  | ELLEN B. DONATO, Ed. D. CESO III
|  | RPFC, PFSEU |  |  |  |  | Director IV
Conforme:
___________________
HGW=3 Engineering & Construction
( siganture over printed name)
______________________
Date
[7 empty] | april 29 | 2
[7 empty] | may 31 | 31 | 9
[7 empty] | jun 30 | 30 | 30
[7 empty] | july | 31 | 31
[7 empty] | Aug | 31 | 20
[8 empty] | 125 | 90

## RepairES-HGW=3
EVALUATION SHEET
Package |  |  | : | CY 2011
Project Title |  |  | : | Repair & Rehabilitation of Building 1,2,3 & Guard House
Location |  |  | : | DepeD-CAR Regional Office, Wangal, La Trinidad, Benguet
Contractor |  |  | : | HGW=3 Engineering & Construction
Subject |  |  | : | Secondary Time Extension
I. | CONTRACT DATA
| Contract Amount |  |  |  | : | Php 916,186.96
| Date of Mobilization/Project Started |  |  |  | : | 2012-07-25
| Contract Duration |  |  |  | : | 60 C.D. + 20 C.D. (First Approved Time Extension) |  |  |  |  | jun | 30
| Original Contract Expiry Date |  |  |  | : | 2012-08-25 | (October 13, 2012 First Extension) |  |  |  | july | 31 | 29
Approved Contract Time Extension no. 1 due to
|  | limited source/fabrication of materials |  |  | : | 20 C.D.
Revised Contract Expiry Date due to
|  | limited source/fabrication of materials |  |  | : | 2012-11-02
II. | SUMMARY OF EVALUATION OF CONTRACT TIME SUSPENSION
| A. | Justification
The Contract Time Extension is in view of the consideration to the letter request of the contractor.
His request is due to limited source/fabrication of materials (Bronze Letters in Building No. 2, Stephen
N. Capuyan Hall).
| B. | Evaluated Contract Time Suspension
Breakdown of Contract Time Extension :
|  | Due to limited source/fabrication of materials | [5 empty] | 20 C.D.
20 C.D.
Prepared by:
Engr. CULLEN S. WEGIYON
PFSEU
|  | Recommending Approval: | [5 empty] | Approved:
|  | VENANCIO P. BALOS | [5 empty] | ELLEN B. DONATO, Ed. D. CESO III
|  | RPFC, PFSEU | [5 empty] | Director IV
Conforme:
___________________
HGW=3 Engineering & Construction
( siganture over printed name)
______________________
Date
[8 empty] | april 29 | 2
[8 empty] | may 31 | 31 | 9
[8 empty] | jun 30 | 30 | 30
[8 empty] | july | 31 | 31
[8 empty] | Aug | 31 | 20
[9 empty] | 125 | 90

## RepairTAR-HGW=3
long bond
CONTRACT TIME ADJUSTMENT REQUEST
Request No. 1
I. | CONTRACT DATA
| Cluster |  |  |  |  | : |  | CY 2011
| Project Title |  |  |  |  | : | Repair and Rehabilitation of Building 1,2,3 & Guard House
| Location |  |  |  |  | : | DepED-CAR Regional Office, Wangal, La Trinidad, Benguet
| Contractor |  |  |  |  | : | HGW=3 Engineering & Construction
| Contract Amount |  |  |  |  | : | Php 916,186.96
II. | NATURE OF REQUEST
| Requesting Party |  |  |  |  | : |  | HGW=3 Engineering & Construction |  |  |  | Requested No. of Days |  |  |  | : | 20 C.D.
|  | A. | Due to Non-payment | [9 empty] | B. | Due to Bad Weather Condition/Other
conditons
|  |  | Billing No. | [5 empty] | : |  |  |  |  | Required Supporting Papers |  |  |  | :
|  |  | Date of Confirmation of SWA | [5 empty] | :
|  |  | Gross Amount | [5 empty] | : | [5 empty] | Approved Construction Schedule
Construction Logbook
Weather Chart
|  |  | Required Supproting Papers | [5 empty] | : | [5 empty] | Certificate from PAGASA, if necessary
Contractor's Project Engineer Report
|  |  |  | Copy of LDDAP | [10 empty] | Certified by DepEd Project Engineer and Noted
|  |  |  | Copy of Official Receipt | [10 empty] | by the Owner
|  |  |  | Copy of Confirmation of SWA | [10 empty] | Progress Photos/Site Photos
| X | C. | Others
|  |  | Reasons |  | : | Due to limited source/fabrication of materials (Bronze Letters in Building No. 2, Stephen
N. Capuyan Hall).
(Please see attached letter request for contract time suspension of contractor.)
|  |  | Required Supproting Papers | [5 empty] | : | (As required by the Owner)
III. | APPROVAL
| Engineer's Evaluation | [5 empty] | : | 20 C.D. |  |  | Recommendation |  |  |  |  | : | Time suspension
[11 empty] | Recommended No. of Days : | [5 empty] | 20 C.D.
| Evaluated No. of Days | [5 empty] | : | 20 C.D. |  |  | Revised Completion Date |  |  |  |  | : | November 2, 2012
| Evaluated by: | [12 empty] | Recommended by:
| Engr. CULLEN S. WEGIYON | [12 empty] | VENANCIO P. BALOS
| PFSEU | [12 empty] | RPFC, PFSEU
| Conforme: | [12 empty] | Approved by:
| HGW=3 Engineering & Construction | [12 empty] | ELLEN B. DONATO,Ed.D., CESOIII
| Contractor | [12 empty] | Director IV
Attachments |  |  |  | :
1. | Contractor's Letter Request
2. | Engineer's Evaluation Sheet
3. | Other Necessary Supporting Documents