## Sheet1
|  | 2021 | [5 empty] | 2022
|  | July | August | September(20) | Octoboer(21) | November(20) | December(11) | January(21) | February(15) | March(22) | April(18) | May(22) | June(21)
Proficiency Test | SKA (July 30) *Result Announcement: August 24
Batch 5 (40 new teachers from 20 schools of 3 islands) | Recruiting
Training (1)
Training (2)
Refresher | Basic (1)
Counselling (For Batch 1 - 3)
Basic (2)
Intermediate (1)
Batch 5 Training
Subject | 40 new teachers
Period | 22 Sep 5 - '23 Jun 30
Schedule | M-F 8:00 - 12:00 (4H)
Target Training Hours | 764H*
* 191 training days x 4H
Refresher
Subject | Batch 1-3 (46)
Period | 22 Sep 5 - '23 Jun 30
Schedule | M-F 8:00 - 10:00 (2H)
Target Training Hours | 120H*
* 60 training days x 2H
** Refresher group will be divided based on the SKA test result and personal preferecne for those who didn't take SKA.
*** Individual teacher can also schedule a counselling with the Korean native teacher after the training hours. The counselling month (December) includes special classes for all as well as online cultural activities.
Year 2022-2023 Holidays
2022
November 1 | All Saints' Day (PH)
November 30 | Bonifacio Day (PH)
December 8 | Feast of the Immaculate Conception (PH)
December 19 ~ 31 | Christmas Break (DepEd)
2023
January 1 ~ 2 | Christmas Break (DepEd)
February 6 ~ 10 | Middle Break (DepEd)
March 1 | Independence Movement Day (KR)
April 6 | Maundy Thursday (PH)
April 7 | Good Friday (PH)
May 1 | Labour Day (PH)
June 12 | Independence Day (PH)